## UPR IP MASTER PLAN
Recommendations |  |  | Objective | Actions | Implementation Period | NDP Priority | Related SDGs | Documents in place (Policies, Acts. Action Plan ) | Baseline | Lead Implementing Entity | Supporting Partners | Progress Indicators | Progress(% execution) | Comment on status action item(key points of achievements and limitations)
Theme: |  | Poverty Reduction
Targets:
1) |  | Reduce percentage of people living in poverty from 58.9 percent (EHIES 2017) to at least 54 percent by 2027
2) |  | Reduce percentage of people living in extreme poverty from 20.1 percent (EHIES 2017) to at least 17 percent by 2027
3) |  | Reduce the working poor from 38.9 percent (EHIES 2017) to at least 34 percent by 2027
4) |  | Improve the multidimensional poverty index from 0.081 (HDR,2016) to 0.05 in 2027.
5) |  | Reduce child poverty rate from 56.5% (CCPA,2018) to 40% in 2027.
118.132 - UPR, CRC |  |  | Address Poverty with a focus on the people living in rural areas and informal settlements in urban areas | 1. Conduct a poverty analysis and mapping poverty stricken community | 2023-2025 | Sectoral Outcome 7.5 | SDG 1 | Poverty trends 2020, EHIES | Poverty trends 2020 | Ministry of Economic Planning & Development | Development Partners | Poverty Analysis and Mapping in place
|  |  |  | 2. Review and implement a National Poverty Reduction Strategy Action Plan with a special focus on the most vulnerable groups |  | Sectoral Outcome 7.5 | SDG 1/2 | 2015 Poverty Reduction Strategy and Action Plan | 2015 Poverty Reduction Strategy and Action Plan | Government central Agencies (MoF, MEPD & MOPS) | NGOs – Food Security Consortium | Revised PRSAP in place and being implemented
[7 empty] | SDG 1 | Budget Estimate books |  |  | Development Partners | Increase share of budget to poverty reduction programmes
|  |  |  | 3. Increase budget allocation to poverty reduction programmes (5%) |  | Sectoral Outcome 7.5 | SDG 1,5,8 | MOYSC and DPMO Strategies and Annual reports
|  |  |  | 4. Strenghten youth and women empowerment (aren't these captured on the poverty reduction strategy?) Where does the youth development fund fit in? |  |  | SDG 13 | MTEA Annuals Reports
5. Improve adaptation to climate change (it has no direct link, find a place for it)
118.128 - UPR |  |  | Promote social policies that increase the quality of life of the people,in particular of the most vulnerable sectors | 1. Revise and operationalise policies and guidelines on accessing adequate social protection grants and eliminate non-eligible recipients. | 2023-2025 | Sectoral Outcome 6.8 | SDG1, 3, 4, 5 | MOH and DPMO Policy documents |  | Deputy Prime Minister’s Office- Social Welfare Department | Development Partners, Ministry of Labour, Ministry of Finance, Ministry of Economic Planning | Number of policies and guidelines revised and implemented
|  |  |  | 2. Ensure that all children born in Eswatini are registered at birth and obtain PINs to access Government services especially education, health and social assistance programmes |  |  |  | Civil Register/ Vital Statistics |  | Ministry of Home Affairs | Ministry of Health and Ministry of Tinkhundla | Proportion of children registered at birth annually
|  |  |  | 3. Conduct community sensitization sessions awareness raising on birth registration at grassroots. |  | Sectoral Outcome 6.8 | SDG 10.5 | Civil Register/ Vital Statistics |  | Ministry of Home Affairs |  | Number of sensitization/ awareness raising session conducted
Theme: |  | Ensure the right to health
Targets:
1 |  | Reduce maternal mortality rate from 452 (Population Census,2017) to 300 per 100,000 live births
2 |  | Reduce newborn deaths from 20 (MICS,2014) to 15 per 100 live births
3 |  | Reduce under 5 stunting from 25.5% (MICS,2014) to 20%
4 |  | Reduce HIV incidence from 1.36% (SHIMS 3,2022) to 0.4%
5 |  | Reduce risk of premature mortality from cardiovascular diseases, cancer, diabetes, and chronic respiratory diseases from 21%(NCD,2022) to 20%
118.140,118.141 - UPR,CEDAW,CRC,ACHPR |  |  | Enhance access to health care and programmes to address non-commucable diseases | 1. Conduct a robust resource mobilisation exercise under the health financing strategy to strengthen health care system. | 2023-2026 | Sectoral outcome 6.1 | SDG 2,3 | MOH Financial Reports | 12.5% of National Budget for Health Allocation | Ministry of Health, Development and implementing partners | Development and health service implementing partners | Resources (financial and otherwise) obtained – 15% of National Budget
|  |  |  | 2. Increase awareness on social behaviour issues that inform development of NCDs, early detection and prompt treatment of non-communicable diseases like mental health, cancer, diabetes to name a few. |  |  |  | STEPS SURVEYS and community demand creation annual reports |  |  |  | Increase in the number of communties where awareness has been raised
3. Conduct an assessment on comorbidity and cophamaceutical link to NCDs
118.146, 118.147,118.148 - UPR, CRC, ACHPR |  |  | Accelerate efforts to reduce maternal and neonatal mortality rates in health facilities and improve access to sexual and reproductive health services | 1. Invest in the retention of skilled health providers within key departments of maternal and neonatal child health services |  |  |  | MOH Retention Policy MICS, MOH training reports, staff deployment ratio |  |  |  | Skill birth delivery coverage, number of skilled midwives and different maternal child health thematics,
|  |  |  | 2. Invest in the availability and functionality of essential maternal neonatal child health equipment,drugs , and supplies in all level health facilities |  |  |  | RESSA |  |  |  | Number of health facilities with adequate neo maternal and functional equaipment and medical supplies
|  |  |  | 3. Increase SRH services to all adolescents for reduction in unintended pregnancies, exposure to STIs, increase use of contraceptives and treatment of infertility/sexual dysfunction. |  |  |  | MICS and SRH Annual reports |  |  |  | Proportion of unintended pregnancies , STIs, contraceptives uptake, infertility/sexual dysfunction amongst adolescent.
|  |  |  | 4. Conduct community awareness and demand creation for good health seeking behaviours on key SRH services which includes early access to health facilities for pregnancy monitoring and child birth |  |  |  | MOH Development partner reports such as Dreams on wheels, PACT |  |  |  | Decrease in maternal and neonatal mortality rate
|  |  |  | 5. Increase services uptake on contraceptives, STI management, sexual dysfunction/infertiliy management for IPV and GBV |  |  | SGD 3, 4 | MICS and SRH Annual reports |  |  |  | Proportion/ number of contraception uptake, STI, sexual dysfunction, infertility, IPV, GBV.
Theme: |  | Promote the right to education
Targets
1 |  | Completion rate (primary education, lower secondary education, upper secondary education)
| 2 | Gross intake to the last grade (primary education, lower secondary education)
3 |  | Improve access to education for children with special needs and disabilities
118.159,118.160, 118.214, 118.215 - UPR, CRC,CEDAW,ACHPR |  |  | To promote the right to education for all children. | 1. Strengthen the implementation of programmes to facilitate access to inclusive primary and secondary education, reduce repetition and increase retention address drop - outs etc. | 2023-2026 | Sectoral outcome 6.2 | SDG 4 | Annual Education Census report: EDSEC, 2018: Repetition Strategy; Ministry of Education Training Sector Policy and Guidelines for the Prevention and Management of Learner Pregnancy, 2022 (EUP, 2022) |  | Ministry of Education and Training | Development partners | 1. Increase in the enrolment rate (disaggregated by age, gender, disability)
|  |  |  | 2. Improve enrolment rates by removing obstacles to acess free primary education | [7 empty] | 2. Increase in retention and completion rates (disaggregated by age, gender, disability).
3. Strengthen re-intergration program for pregnant girls
|  |  |  | 4. Strengthen and upscale programs supporting children with special needs and disabilities | [7 empty] | 3. Increase of programs for children with special needs and disabilities
Theme: |  | Promote the right to clean water and sanitation
Targets:
1 |  | Increased access to safe/potable water by 10% (annual increase by 2%) of households
| 2 | Increased national water coverage from 75.6%(EHIES,2017) - 80% households
| 3 | Increase access to safe water in rural, informal and peri-urban areas from 49% (EHIES)to 65% of households
| 4 | Increased access to improved household sanitation from 53% (MICS,2014)to 85%
| 5 | Reduce open defacation from 11%(MICS 2014) to 5% by 2024 and eliminate by 2027
| 6 | Increased percentage of people practising appropriate and sustained hygiene behaviour from 26%(MICS,2014) to 50% by 2027
| 7 | Improve water availability through the construction of at least 2 new multi - purpose dams
8 |  | Review Water Act 2003 to strengthen the governance of water supply in the country - activity
118.136, 118.137,118.138 - UPR, CRC |  |  | Continue to take the necessary measures to improve access to safe and clean drinking water and sanitation facilities to the vulnerable population | 1. Effectively and efficiently manage and regulate water resources | 2023-2026 | Sectoral Outcome 6.3 | SDG 6 | EHIES, MICS, WASH Reports, HOH Enviromental annual Reports, MNRE annual reports | (tatgets) | Ministry of Natural Resources and Energy and Ministry of Health | WASH Forum Members and Development Partners | Proprtion of the population with access clean and safe water
|  |  |  | 2. Effectively and efficiently manage WASH services and infrastructure | [7 empty] | Proportion of the population with access to safely managed sanitation facilities.
|  |  |  | 3. Increase access to adequate and safe/potable water, sanitation and hygiene | [7 empty] | Proportion of the population with access to handwashing facilities
4. Strengthen WASH governance and empowerment of citizens
Theme |  | Ensuring the rights of special groups (Stateless Persons, Persons with Disabilities, Gender Justice, Child rights)
Targets:
1) |  | Increase in the number of civic registrations
2) |  | Increased knowledge to accommodate pupils with albinism
3) |  | Increased participation of these groups in climate change and disaster risk spaces
4) |  | Reduction in incidences of GBV cases
5) |  | Reduce systematic social exclusion of sexual and gender minorities
118.27 - UPR, ACHPR, Maputo Protocol, ICCPR, CEDAW,CRC,ACRWC |  |  | To ensure that all citizens are registered within the national registry system and to ensure no persons are stateless | 1) Raise awareness on issues affecting stateless persons | 2023-2024 | Sectoral Outcome 7.1 | SDG 1,16 | 1) National Statelessness Action plan |  | Ministry of Home Affairs; | DPMO, MOH,CSOs, MTAD, Development Partners | 1) Number of campaigns addressing the issue of statelessness disaggregated by region, medium of communication, and target audience disaggregated by sex, age
|  |  |  | 2) Conduct a study on stateless people in Eswatini |  |  |  | 2) BMDs Act (birth marriage and death) |  |  |  | 2) Study on Stateless Persons in Eswatini Report
|  |  |  | 3) Review Civil Registration laws to increase access for stateless people in Eswatini to acquire citizenship |  |  |  | 3) Civic registration |  |  |  | 3) Revised Immigration law approved by parliament in place
|  |  |  | 4) Roll out mop up campaign for civil registration |  |  |  | 4) Mop up Campaign Plan |  |  |  | 4) Resource mobilization strategy in place and operational and functional funding scheme
|  |  |  | 5) Develop a Resource Mobilization Strategy for registration of vulnerable groups. Have a funding scheme that can assist vulnerable groups in the registration processes | [5 empty] | DPMO |  | 5) Number of civic registrations annually and mop campaigns
|  |  |  | 6) Enforce the implementation (Section 20(1) (2)(3) of the Births Marriages and Deaths Act to achieve universal birth registration (MoU between MOHA&MOH) | [7 empty] | 6) MoU between MOHA&MOH in place
118.59 - UPR, CEDAW, CRC, ICCPR |  |  | To ensure that people with albinism are protected and have access to education and medical services | 1) Awareness raising on the rights and welfare of PWDs especially Persons with Albinism | 2023-2025 | Sectoral Outcome 6.8 | SDG 3,4,10,16 | PWDs Act 2018 |  | DPMO | MOH, MOET, FODSWA, OPDs | 1) Awareness raising campaigns conducted disaggregated by region, mode of communication used and target audience by sex and age
|  |  |  | 2) Improve registration and support to PWDs - Establishment of the registry for PWDs, including PWA |  |  |  | PWD Regulations, Education and Training Sector Policy (2018), Education Sector Strategic Plan (2022-, Multi Year Plan of Action (2022-2025) |  |  |  | 2) Registry for PWDs in place and Operational
|  |  |  | 3) Provide legal assistance to PWDs. | [7 empty] | 3) Proportion of PWDs accessing legal assistance disaggregated by rights violated, sex and age
|  |  |  | 4) Provide support to increase access to education with appropriate learning materials, assistive devices and trained educators. | [7 empty] | 4) (1) Number of persons with albinism provided with appropriate education, assistive devices (2) Number of educators trained. Propotion of Inclusive Schools in Eswatini
|  |  |  | 5) Provide health care accessories for persons with Albinism | [7 empty] | 5) Proportion of Health facilities with health care accessories for Persons with Albinism
|  |  |  | 6) Fully operationalise the PWD Act of 2018 | [7 empty] | 6) Statutory bodies for PWDs appointed and operational
118.197 - UPR |  |  | To ensure inclusive participation and involvement of women and children and PWDs and local communities in design and implementation of climate change and disaster risk reduction framework | 1) Identify and mobilize these different groups into the development and implementation platforms of climate change and disaster | 2023-2024 | Sectoral Outcome 6.8 | SDG 1,5,11,3 | National determined contributions (NDC) |  | Ministry of Tourism and Environmental Affairs - Climate Change Unit | MNRE, NDMA, Red Cross, DPMO, Humanitarian Partners | 1) Proportion of; women, children, PWDs and local communities’ participating/represented in climate change and disaster risk reduction platforms
2) Prioritization of vulnerable groups in responding to rescue operations of climate change and disaster risk.
3) Strengthen the early warning systems to integrate the vulnerable groups as well as populations at risk
118.61,118.76, 118.164, 118.169, 118.173 - UPR, CEDAW |  |  | Increase public awareness to end violence | 1) Conduct public awareness campaigns targeted on the SODV Act including Gender Based Violence | 2023-2024 | Sectoral Outcome 6.6 | SDG 1, 5,16 | SODV Act |  | DPMO | MOJCA, MoH, REPS, CSO’s | 1) Awareness raising campaigns conducted, disaggregated by region, mode of communication used and target audience by sex and age
|  |  |  | 2) Produce and disseminate a simplified version of the SODVA in accessible formats |  |  |  | Simplified version of the Act |  |  |  | 2) Number of Distributed Simplified SODVA by target audience disaggregated by sex and age
|  |  |  | 3) Put in place and operationalise institutions & mechanisms mentioned in the Act for implementation (Offenders register, |  |  |  | Translated version of the SODVA in Siswati and Braille available |  |  |  | 3) Statutory bodies under the SODVA established and operational
|  |  |  | 4) Conduct continuous capacity building for duty bearers on the SODVA |  |  |  | Guidelines for Shelters of GBV survivors developed |  |  |  | 4) Number of capacity building initiatives conducted disaggregated by duty bearers, by sex
|  |  |  | 5) Provide protection and comprehensive services for GBV survivors | [7 empty] | 5) Number of One Stop Centres operational and decentralised by region 6) Number of GBV Survivor Shelters operational and decentralised by region
118.61 - UPR, ICCPR |  |  | To promote inclusivity ,diversity and equality of sexual and gender minority | 1) Conduct capacity building for frontline workers on Sexual Orientation, Gender Identity and Expression (SOGIE) | 2023-2025 | Sectoral Outcome 6.6 | SDG 3,4,10,16 | Constitution; Section 20 |  | DPMO | MoH, MoET, REPS, MoJCA | 2) Number of capacity building initiatives on SOGIE conducted disaggregated by duty bearers and sex
SODV Act
Theme: |  | Strengthening the promotion and protection of human rights
Targets
1 |  | An independent National Human Rights Institution strengthened
2 |  | Legal Aid Office fully operational
118.46, 118.45, 118.48, 118.49, 118.51-118.56 - UPR, CEDAW, ICCPR, ACHPR |  |  | To comply with international human rights standards | 1. Adopt enabling legislation compliant with Paris principles: (Guarantee financial independence of the Commission and restructuring). | 2023-2026 | Sectoral Outcome 4.2 and 7.3 | SDG 16 | Human Rights Bill |  | Ministry of Justice | Ministry of Public Service and Ministry of Finance | Human Rights legislation in place.
|  |  |  | 2. Strengthen human and financial resources of the Commission | [7 empty] | Independent Human rights Commission restructured and strengthened
3. Develop Strategic frameworks for the Commission
118.43 and 118.128 - UPRCEDAW, ICCPR, ACHPR, Maputo Protocol |  |  | To enable access to justice for the indigent people. | 1. Operationalise the Legal Aid Office | 2023-2026 | Sectoral Outcome 7.3 | SDG 16 | Legal Aid Bill, Amended Legal Practitioners Act | Legal Aid Need Eswatini Baseline Survey | Ministry of Justice | Ministry of Public Service and Ministry of Finance | Legal Aid Act in place
|  |  |  | 2. Finalize the Legal Aid Bill | [7 empty] | Amended Legal Practioners Act
|  |  |  | 3. Establish the Legal Aid Fund | [7 empty] | Legal Aid Fund
Theme: |  | Promotion and protection of the right to freedom of opinion, expression & access to information
Targets:
1) |  | Increased knowledge on fundamental rights and responsibilities
2) |  | Decreased allegations of human rights violations (decreasing allegations does not look appropriate as a target)
118.98, 118.101, 118.105, 118.107, 118.111, 118.112, 118.220 - UPR, ICCPR,ACHPR |  |  | 1. Promote freedom of the press, | 1. Raise awareness to members of the public on rights and responsibilities | 2023-2025 | Sectoral Outcome 7.4 | SDG 16 | 1. Kingdom of Eswatini Draft Media Policy |  | Ministry of ICT | Commission on Human Rights and Public Administration, Parliament, Media (Editor’s forum), Civil Society Organisations | 1) Awareness raising campaigns conducted disaggregated by region, mode of communication used and target audience by sex and age
|  |  |  | 3. Align laws with the Constitution to promote the rights to Freedom of the Press (finalize: The Access to Information Bill, Media Commission Bill,The Eswatini Broadcasting Bill) |  |  |  | 2.The Access to Information Bill (also known as Freedom of Information Bill) has now been gazetted, ready to be deliberated upon by Senate and the House of Assembly |  |  |  | 2) Sensitization, training, undertakings, disaggregated by topics covered, duty bearer reached and by sex
|  |  | 2. Ensure the protection, respect and fulfilment of press freedom, and the rights and safety of journalists. | 4.Strengthen and capacitate duty bearers, media personnel on the right to freedom of opinion, expression and access to information in relation to Eswatini legal frameworks. |  |  |  | A Media Commission Bill whose object is to promote and establish an equitable balance between the constitutional guarantees of freedom of the press and the protection and respect of the rights to privacy is under review. |  |  |  | 3) Legal Frameworks reviewed in line with the Constitution
|  |  |  | 5.Adopt journalism good practices that operate with professional ethics and self-regulatory principles. |  |  |  | Eswatini Broadcasting Act no. 7 of 2023 |  |  |  | 4) Number of knowledge-sharing and capacity-building sessions held with the Media on Eswatini Legal Frameworks relating to Freedom of Expression, Opinion, and access to Information
Theme: |  | Prohibition against Torture
Targets:
1) |  | Increased knowledge on fundamental rights and responsibilities
2) |  | Decreased allegations of torture by law enforcement agencies
118.21, 118.79, 118.88 118.89 - UPR, ICCPR,ACHPR |  |  | To prevent and eradicate the use of torture and other cruel, inhuman and degrading treatment or punishment and ensuring accountability for acts of torture | 1.Capacitate law enforcement officers on Human rights; review of training curriculum ( for newly recruited officers and long serving officers), Conduct Train the Trianers Courses frequently on basis of human rights ToT (training of trainers) Training of upper level and lower management officers on Human rights and dignity | 2023-2025 | Sectoral Outcome 10.1 | SDG 16 |  |  | Prime Minister’s Office (Police) | MoJCA, Correctional Services, UEDF, Parliament, CHRPA, Judiciary, CSOs | 1) Capacity-building initiatives undertaken for law enforcement officers on human rights disaggregated by department, or ranks, numbers reached, by sex
|  |  |  | 2. Establish an Independent Complaints Commission to investigate allegations of torture or other ill-treatment which may be alleged against law enforcement agencies. | [7 empty] | 2) An established Functional Independent Complaints unit/Mechanism for reporting and investigation of cases/allegations of torture and ill-treatment by law enforcement officers
|  |  |  | 3.Develop a clear procedure for receiving complaints of human rights violations | [7 empty] | 3) A Clear and functional complaints reporting mechanism established and accessible to all citizens in their diversity
|  |  |  | 4. Strengthening an accountability mechanism for perpetrators of torture and ill-treatment of public within the law enforcemnt agencies | [7 empty] | 4) An established and functional accountability mechanism for perpetrators of torture and ill-treatment of public
Theme: |  | Ensuring favorable conditions of detention centres
Targets:
1) |  | Improved conditions of detention centres
2) |  | Reduced overcrowding in prisons
118.94, 118.95 118.96 - UPR, ICCPR,CRC,ACHPR |  |  | To improve conditions of detention centres to ensure full enjoyment of rights by detainees | 1.Strengthen the regular assessment of the conditions of detention centres in the country. | 2023-2025 |  | SDG 16 |  | Ministry of Justice/ His Majesty's Correctional Services bulletins | HMCS | MoJCA, REPS, CSOs, Judiciary | 1) Assessment report of detention Centres in Eswatini with Clear recommendations available
|  |  |  | 2. Revive the Criminal Justice Stakeholders forum to address challenges obtaining in detention centres | [7 empty] | 2) Proportion of detainees in detention centres of Eswatini against the total prison population. An indicator would be improved structures for detainees
|  |  |  | 3. Allocate necessary resources to renovate prisons and other detention centres | [7 empty] | 3) Total Expenditure over budget allocated to renovation and maintenance of Prisons and detentions centers annualy
|  |  |  | 4.Explore other alternatives to imprisonment | [7 empty] | 4) Active and resourced alternative programs to imprisonment for corrections and diversions to imprisonment
|  |  |  | 5.Take measures to accommodate detainees with special needs | [7 empty] | 5) Proportion of detention centres with facilities to accommodate detainees with special needs. Improved structures for detainees and inmates with special needs. Eg wheel chair pathways constructed.
Theme: |  | Promotion of the right to peaceful assembly
Targets:
1 ) |  | Continous capacitations of law-enforcers on the rights to peaceful assembly
2) |  | Decrease in incidences of violent strikes
118.97, 118.102, 118.108, 118.110, 118.114, 118.222 - UPR, ACHPR,ICCPR |  |  | 1. To promote and protect public order | 1. Raise public awareness on the right to peaceful assembly (Public Order Act no. 12 of 2017) Public Order and Industrial Relations Act no.1 of 2000 and The Code of Good Practice, Urban Government Act 1969. | 2023-2025 | Sectoral Outcome 7.4 | SDG 16 | Within the limits of the budgetary allocations |  | Ministry of Labour, Law enforcement / Police &Correctional Services officials/MoJCA | Civil Society Organizations | Reduced incidents of violent protests.
|  |  |  | 2. Capacitate social partners agencies on management of public gatherings in line with relavant Legislation. |  |  |  | Public Order Act no. 12 0f 2017 and Industrial Relations Act no.1 of 2000 and The Code of Good Practice. |  |  |  | Peaceful public protests. Improved rate of compliance with the applicable laws.
3.Create platforms for a genuine, inclusive and comprehensive dialogue with all relevant stakeholders or social partners
Urban Government Act 1969
Theme: |  | Ratification of and accession to International Instruments
Targets:
1) |  | Stakeholder consultations on the ratification Instruments
2) |  | Deposition of Ratification/Accession Instruments
118.11,118.12, 118.13,118.14, 118.15 - UPR, (ratification of Opt CEDAW),CEDAW |  |  | Ensure commitment to promote and protect human rights at International level | 1. Issue instruction to MoFAIC to ratify the Outstanding and Supported Instruments (OP CAT, OP CEDAW. | 2023-2024 | Sectoral Outcome 7.3 | SDG 16 | National Budget |  | PM's Office, DPMO | PM's Office, DPMO | DPMO Memo to MoFAIC to accede to OP CEDAW
MoJCA Memo to MoFAIC to accede to OP CAT
2. Conduct Consultations towards the Convention on the Prevention and Punishment of the Crime of Genocide
[10 empty] | MoFAIC |  | MoFAIC to accede to Convention on the Prevention and Punishment of the Crime of Genocide
Theme |  | Compliance with treaty body reporting obligations
Targets
1 |  | Submit overdue reports to treaty bodies
2 |  | Follow -up on the implementation of recommendations from human rights mechanisms
3 |  | Establish an online tracking database
118.33 - UPR |  |  | To comply with the country's reporting obligations | 1. Strenghten NMRF Secretariat and Committee | 2023-2026 | Sectoral Outcome 7.3 | SDG 5 & 16 | National Budget |  | Ministry of Justice | Ministry of Public Service and Ministry of Finance | Reduced backlog of outstanding reports
2. Develop and adopt a UPR Recommendations Implementation Plan
3. Develop a NMRF Strategy
|  |  |  | 4. Submit outstanding reports: Prioritize initial reports (CAT, ICESCR) and periodic reports | 2023-2026 |  |  |  |  | Ministry of Justice | MoF, MoEPD
Note on E68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 & 2 fit into 4
Note on E131: Administrator: Keep in mind of the four key measurement task around: * Training on prevention of Torture ** Training on Crowd Management *** Training on evidence gattering on Gender Based Evidence **** Basic Safeguard on liberty and security purposes
Note on W1: Administrator: If the ministery has no baseline, kindly leave it blank
Note on AJ124: N.M.R.F Sphiwe: consider action 3 that highlights the legal frames
Note on BB1: Administrator: SCALE YOUR EXECTUTION OF THE PROGRAM AND THE TASKS OVERALL PROGRESS…USE PERCENTAGES

## UPR IP COSTED
THEME | RECOMMENDATIONS | RELATED TREATY BODY RECOMM. | OBJECTIVE | ACTIVITIES | DELIVERABLES | INDICATORS | LEAD MINISTRY | IMPLEMENTING MIN. & PARTNERS | TIMELINE | RESOURCES | BUDGET TOTAL | NDP PRIORITY | RELATED SDGS | DOCUMENTS IN PLACE (Policies, Acts, Action Plans)
Poverty reduction and social protection grants
1. Reduce percentage of people living in poverty from 58.9 percent (EHIES 2017) to at least 54 percent by 2027
2. Reduce percentage of people living in extreme poverty from 20.1 percent (EHIES 2017) to atleast 17 percent by 2027
3. Reduce working poor from 38.9 percent (EHIES 2017) to at least 34 percent by 2027
4. Improve the multidimensional poverty index from 0.081 (HDR, 2016) to 0.05 in 2027
5. Reduce child poverty rate from 56.5% (CCPA, 2018) to 40% in 2027
POVERTY & SOC. GRANTS | 118.132 - UPR |  | Make efforts to reduce poverty in the country | Fast track poverty analysis by publishing the Income & Expenditure Survey | National Poverty Analysis and Mapping Report | Development of evidence informed programs to address poverty | Min of Economic Planning & Development | Central Statistics Office | 2024-12-01 | Enumerators and research related costs | E300,000 | Sectoral Outcome 7.5 | SDG 1 | Poverty trends 2020, EHIES 2015 Poverty Reduction Strategy and Action Plan
|  |  |  | Increase by 5% the budget allocation to poverty reduction programmes; and periodically review the implementation progress of the National Poverty Reduction Strategy Action Plan | National budget monitoring report 2 year inter-ministerial progress report on poverty alliviation | 5% budget increase to poverty reduction programs Qualitative evidence of, and quantitative (percentile disaggregated data) decrease on the level of poverty | MEP&D | All relevant Ministries (as tasked on the NPRSAP) | 2024, 2026 | MEP&D Personnel (Staff time) | E28,800 (E480 x 30 people x 2 meetings) Annual interministrial review meeting | Sectoral Outcome 7.5 | SDG 1,5,8 | Budget Estimate books Ministrieal Reports
|  |  |  | Revise and operationalise policies and guidelines on accessing adequate social protection grants and eliminate non-eligible recipients | Policies and guidelines on accessing social protection grants revised, and receiptient database revised | Social protection grants disbursement is administered through policies and guidelines | DPMO | MoJCA, MoH, & DPMO | 2024 - 2025 | DPMO Personnel (staff time) Interministrial review meetings. | No related costs 4 meetings X 100 per person X number of participants | Sectoral Outcome 6.8 | SDG1, 3, 4, 5 | MOET, MOYSC and DPMO Strategies and Annual reports
Ensure enjoyment of the right to health
1. Reduce maternal mortality rate from 452 (Population Census,2017) to 300 per 100,000 live births
2. Reduce newborn deaths from 20 (MICS,2014) to 15 per 100 live births
3. Reduce under 5 stunting from 25.5% (MICS,2014) to 20%
4. Reduce HIV incidence from 1.36% (SHIMS 3,2022) to 0.4%
5. Reduce risk of premature mortality from cardiovascular diseases, cancer, diabetes, and chronic respiratory diseases from 21%(NCD,2022) to 20%
HEALTH | 118.140,118.141 - UPR | 34 and 35 CEDAW 28 and 29 ICCPR 54 CRC paras 51 (b), 53, 55 ACERWC paras 22, 36, African Charter 71 | Enhance access to health care and programmes to address non-communicable diseases | Conduct a robust resource mobilisation exercise under the health financing strategy to strengthen health care system. | Health Financing Strategy implemented Improved access to health care service for NCD patients | Number of resource mobilisation activities Increased access to health care by NCDs patients Reduction in NCD mortality, morbidity, and complications | MoH | MOEPD | 2024 - 2025 | MoH Personnel (Staff time) |  | Sectoral outcome 6.1 | SGD 3 | MOH Financial Reports
|  |  |  | Increase awareness on social behaviour issues that inform development of NCDs, early detection and prompt treatment of non-communicable diseases like mental health, cancer, diabetes to name a few. | Number of awareness raising events held on the subject | Number of people reached by awareness messages Number of people with newly diagnosed NCDs | MOH | Development and health service implementing partners | 2024 - 2025 | Annual airtime with VOC, EBIS, Channel S & Swazi TV | 30 minutes slots, twice a week with VOC at E70,000 (in 2022) |  |  | STEPS Surveys and community demand creation annual reports
|  |  |  | Conduct an assessment on comorbidity and cophamaceutical link to NCDs | Medical assessment report on comorbidity and cophamaceutical link to NCDs | Programmatic interventions developed (treatment reviewed and readapted as per the findings of the assessment) | MoH | MoH | 2024 - 2025 | Medical Personnel (assessment mainstreamed into daily work)
| 118.140,118.141 - UPR | 28, 29 ICCPR 34, 35 CEDAW 54 UNCRC paras | Accelerate efforts to reduce maternal and neonatal mortality rates in health facilities and improve access to sexual and reproductive health services | Invest in the retention of skilled health providers within key departments of maternal and neonatal child health services | Highly skilled and motivated health care providers in the maternal and neonatal child health services | Skilled midwives ratio against annual births in each health centre Perfomance appraisals and incentives introduced Salary reiview for Health Care Workers matching market value | Min of Health | Civil Service Commission | 2024 - 2025 Ongoing | MoH Personnel (Staff time) MoH Personnel (Staff time) | Civil Service Commission to conduct salary review exercise for public servants, espcially front-line responders |  |  | MOH Retention Policy MICS, MOH Training Reports, staff deployment ratio
|  |  |  | Invest in the availability and functionality of essential maternal neonatal child health equipment,drugs , and supplies in all level health facilities | Neonatal child health equipement is avaiable and functional, including supplies | An annual invetory report for all government health facilities 15% increase in allocated budget for equipment and medical supplies shortfalls, including replacement of old, and servicing of available equipment | MOH | Development and Implementing Partners | 2024 - 2026 | MoH & MoEPD Personel (Staff time) |  |  |  | RESAA
|  |  |  | Increase SRH services to all adolescents for reduction in unintended pregnancies, exposure to STIs, increase use of contraceptives and treatment of infertility/sexual dysfunction. | Increased access to comprehensive SRH by adolescents, including GBV clinical management, treatment of infertitility and sexual dysfunction | Frequency of mobile clinics and decentralised access of SRH services % increase in uptake of SRH including contraceptives, STI management, sexual dysfunction/infertiliy management for IPV and GBV | MoH | Health Implementing Partners & Development Partners | 2024 - 2027 | MoH Personnel (Staff time) |  |  |  | MICS & SRH Annual Reports
|  |  |  | Conduct community awareness and demand creation for good health seeking behaviours on key SRH services which includes early access to health facilities for pregnancy monitoring and child birth | Reduction in maternal and neonatal mortality rate | Number of people reached by awareness messages Number of pregnant women seeking antenatal care within the first trimester | MoH | Development and Health Implementing Partners | 2024 - ongoing | Media airtime, IEC materials for nation wide distribution, SRH campaign | E300,000 |  |  | MOH Development partner reports (i.e. Dreams on Wheels by PACT)
Promote the right to education
Completion rate (primary education, lower secondary education, higher secondary education)
Gross intake to the last grade (primary education, lower secondary education)
Improve access to education for children with special needs and disabilities
EDUCATION | 118.159,118.160, 118.214, 118.215 - UPR | 12, 62, 63, 64 - CRC 30 and 31 CEDAW ACHPR | To promote the right to education for all children. | Strengthen the implementation of programmes to facilitate access to inclusive primary and secondary education, reduce repetition and increase retention address drop - outs etc. | All children in their diversity (disability and special needs, pregnancy, OVCs etc) have access to education Reports on programs implemented to increase access and retention of children in school | Reduced % of drop outs from primary to high school Sustained % of enrolment from admission to completion, including children with disabilities, OVCs, pregnant girls | MoET | MoEPD, MoH Development partners, School Committes, Headteachers Association | 2024 - 2027 |  | Allocate 21% of GDP annually | Sectoral Outcome 6.2 | SDG 4 | Annual Education Census Report; EDSEC 2018: Repetition Strategy; Ministry of Training Sector Policy and Guidelines for the Prevention and Management of Learner Pregnancy, 2022 (EUP, 2022)
|  |  |  | Improve enrolment rates by removing obstacles to access free primary education | All children have access to primary education | Increased in retention and completion rates (disaggregated by age, gender, disability) | MoET | MoEPD, Development partners, School Committes, Headteachers Association | 2025 - 2027
|  |  |  | Awareness raising workshops for school committees, headteachers Association, parents, and students on education policies i.e. related to pregnancy & retention | An enabling environment for preg girls retention in school | Reduced % of school drop outs as compared to previous years | MoET | MoH, Development partners & CSO partners | 2024 - 2025 | Media airtime, IEC Materials for nation wide reach to relevant stakeholders, i.e. head teachers, teachers, parents, students and pregnant girls
Promote the right to clean water and sanitation
1. Increased access to safe/potable water by 10% (annual increase by 2%) of households
2. Increased national water coverage from 75.6%(EHIES,2017) - 80% households
3. Increase access to safe water in rural, informal and peri-urban areas from 49% (EHIES)to 65% of households
4. Increased access to improved household sanitation from 53% (MICS,2014)to 85%
5. Reduce open defacation from 11%(MICS 2014) to 5% by 2024 and eliminate by 2027
6. Increased percentage of people practising appropriate and sustained hygiene behaviour from 26%(MICS,2014) to 50% by 2027
WASH | 118.136, 118.137,118.138 - UPR | CRC paras 58, 59, and 61 c. ACERWC para 38 | Continue to take the necessary measures to improve access to safe and clean drinking water and sanitation facilities to the vulnerable population | Increase access to adequate and safe/potable water, sanitation and hygiene | Increased access to adequate, clean/potable water, sanitation and hygine | Number of families with WASH operational infrastructure | MoNRE | MoH, Micro-Projects, Development partners | 2024 - 2027 | WHO Report | 1.5 to 2% of National GDP | Sectoral Outcome 6.3 | SDG 6 | EHIES, MICS, WASH Reports i.e. UNICEF, HOH Environmental Annual Reports, MNRE Annual Reports
|  |  |  | Raise public awareness on practising appropriate and sustained hygiene behaviour | Improved livelihood and health on WASH | Number of people reached by awareness messages | MoH | MoNRE, MoH & WASH CSOs partners | 2024 - 2027 | Media campaign (VOC, EBIS)
|  |  |  | Increase water sources through the construction of at least 2 new multi - purpose dams | Increased clean, adequate, and potable water sources | 2 multi-purpose dams constructed | MoNRE | MoPWT | 2027 | Published by Relief World, titled Swaziland: New Dams to be built to boost irrigation | E280 million budgetted for 3 irrigation dams in 2005
|  |  |  | Review Water Act 2003 to strengthen the governance of water supply in the country | Passed amendment Water Act | Governance of water supply is strengthened | MoNRE | MoJCA | 2024 - 2025 | Staff time
Address statelessness
1. Increased registration of stateless individuals
2. All new births are registered at birth
3. Civil Registration and Vital Statistics Law passed by 2026
4. Funding scheme for birth registration established
STATELESSNESS | 118.27 - UPR | UNCRC para 34 and 35 ACRWC para 25, 26, 42 ACHPR para 76 CEDAW para 29 Maputo Protocol para 82 | To ensure that all citizens are registered within the national registry system and to ensure no persons are stateless | Raise awareness on issues affecting stateless persons | Increased awareness on stateleness, its challenges and impact | Number of awareness raising sessions held Number of people reached | MoHA - Department of Civil Registration and Vital Statistics | Development Partners, CSOs | 2024 - 2025 | Media Campaign (VOC, EBIS) |  | Sectoral Outcome 7.1 | SDG 1 & 16 | National Statelessness Action Plan BMDs Act Civil Registration Database Mop up Campaign Action Plan
|  |  |  | Conduct study on stateless people in Eswatini | A study report on statelessness | Reduced number of stateless person in Eswatini | MoHA - Department of Civil Registration and Vital Statistics | Development Partners | 2024 | Research costs, Researcher and enumerator costs | E300,000
|  |  |  | Continue to roll out the mop-up exercise to Manzini and Hhohho Regions | All people in Manzini and Hhhohho regions are registered | Number of people registered during the mop-up initiative in Manzini and Hhohho regions | MoHA - Department of Civil Registration and Vital Statistics | Development Partners | 2025 | MoH personnel (staff time) | 1900000
|  |  |  | Enforce the implementation (Section 16 & 17) of the Civil Registration and Vital Statistics Act 2023 to achieve universal birth registration (Note: relating to registration of children born of out of wedlock) | All births registered within a day of delivery Increased access to social services by children | Number of births vs number of registered births Unregistred births eliminated by 2026 | MoHA - Department of Civil Registration and Vital Statistics | MoHA partnership with MoH for children's registration at birth | 2026 | Staff time
|  |  |  | Speed up operationalisation of the Civil Registration law to increase access for stateless people in Eswatini to acquire citizenship | Civil Registration enacted into law - addressingg legislative hindrances | Increased number of stateless people acquired citizenship | MoJCA | MoHA/VSCR | 2024 | Staff time
Ensure the enjoyment of rights for persons with disabilities
1. Provide a conduce environment for the enjoyment of rights by persons with disabilities
2. Person's with disabilities are known and documented for proper service delivery
3. All impendiment in the enjoyment of the right to education and access to health are removed.
PWD & PWA | 118.59, 118.211 - 215 - UPR | 39 - CEDAW 27 - CRC 22 & 23 ICCPR | To ensure that people with disability , including those with albinism are protected and have access to education and medical services | Conduct awareness raising on the rights and welfare of PWDs especially Persons with Albinism | Increased public awareness on the rights of PWDs and PWAs Rights of PWDs & PWAs are respected, protected, and fulfilled | Number of awareness raising sessions held, and number of ppeople reached Number of PWDs and PWAs access social and health services | DPMO | MoET, MoH, FODSWA, development partners and CSOs | 2024 | Media campaign |  | Sectoral Outcome 6.8 | SDG 3, 4, 10, 16 | PWDs Act 2018 PWD Act Regulations Education Sector Strategic Plan (2022) Multi-Year Action Plan (2022 - 2025)
|  |  |  | Fully operationalise the PWD Act of 2018 | A developed multi stakeholder implementation roadmap A multi-stakeholder annual review progress report | Costed implementation and a M&E Framework in place An annual multi-stakeholder review meeting on the status of implementation of roadmap | DPMO | Multi-stakeholder Approach/Interministrial | 2024 - 2025 | Consultency fees E480pp X 25 participants X 2 meetings | E150,000 E24,000
|  |  |  | Provide support to increase access to education with appropriate learning materials, assistive devices and trained educators. | PWDs & PWAs have access to quality education | Number & type of learning material provided Number of assistive devices provided for those in need Number of trained educators vs ratio of students | MoET | DPMO, MoEPD/MoF | 2024 - 2027 | Provide budget for i) learning materials, ii) assistive devices, and iii) number of recruited (trained) educators | At least 1% of GDP budget to be allocated to disability in Low and middle income countries (International Disability Alliance) compared to 2.1% in developed countries
|  |  |  | Provide health care accessories for persons with disabilities such as Albinism | Person with disabilities such as albinism have access to health care accessories | Number of PWAs accessing health care accessories | MoH | DPMO & MoEPD, FODSWA | 2025
|  |  |  | Provide legal assistance for PWDs | PWDs rights are protected, and their ability to access justice strengthened | Proportion of PWDs accessing legal assistance disaggregated by rights violated, sex, age, type of disability | Legal Aid Office | MoJCA, DPMO | 2024 - 2027 | Legal Aid Office Personnel
|  |  |  | Establish a registry for PWDs, including PWA | Record of all PWDs & PWAs disaggregated by age, type of disability, sex, level of education etc Fact based planning and sufficient allocation of resources for social services to PWDs | Number of PWDs & PWAs accessing social services services (disaggregate by sex, age, diability, and service received) | DPMO | MoJCA | 2024 | DPMO Personnel (Staff time)
Ensure inlcusive and meaningful participation of women, children, PWDs, and local communities in climate change and disaster management planning initiatives
1. All sectors of society meaningful participate and contribute to climate change and disaster management initiatives
2. Rescue operations prioritise vulnerable groups
Climate Change | 118.197 - UPR | 59 CRC | To ensure inclusive participation and involvement of marginalised groups (women, children, PWDs and local communities) in design and implementation of climate change and disaster risk reduction framework | Identify and mobilize marginalised groups to participate in the development and implementation platforms of climate change and disaster | Marginalised groups included and actively participate in the design and implementation of climate change and DRRF | Total number of each of the marginalised groups participating in climate change and DRR meetings | DPMO | NDMA | 2024 - 2025 | Include marginalised groups, and providing an enabling environment for their participation |  | Sectoral Outcome 6.8 | SDG 5, 11, 13 | National Determined Contributions (NDC) NDMA Policies and Action Plan Disaster Response Framework
|  |  |  | Prioritization of vulnerable groups in responding to rescue operations of climate change and disaster risk. | Rescue operational plan reviewed and demonstrates prioritization of vulnerable groups Resources allocated and staff trained to implement plan | Rescue mission reports attest prioratization of vulnerable groups | DPMO | NDMA | 2024 - 2025 | NDMA Personnel (staff time) - incoperate marginalised groups in rescue plans
|  |  |  | Strengthen the early warning systems to integrate the vulnerable groups as well as populations at risk | Early warning systems strengthening plan | Qualitative and quantitative reports | DPMO | NDMA, Meteorology Dept | 2024 | Staff time | Prepare post disaster situational reprts
Gender based violence
1. All sectors of duty bearers (service providers) are trained on SODVA, and are able to deliver exceptional services by 2027
2. SODVA fully operalinalised by 2027 (relevant institutions and mechanisms in place to ensure full implementation of the Act)
3. Public awareness campaigns on the SODVA reaches 300,000 people by 2026
GBV | 118.27 - UPR | 30 CEDAW 27 ICCPR 43 UNCRC | Increase public awareness to end violence & provide comprehensive services to GBV survivors & victims | Produce and disseminate a simplified version of the SODVA in accessible formats | SODVA simplified knowledge products produced, including braille, audios, & print format | Number of knowledge products produced per format, dissemination records on audience reached (i.e. location, mode of communication, demographics of audience) | DPMO | Development partners, CSOs | 2024 - 2025 | Printing of simplified SODV, including braille, audio production costs | E500,000 | Sectoral Outcome 6.6 | SDG 5, 10, & 16 | SODV Act 2018 Simplified Version of the SODV Act Translated versions of the SODV Act (Siswati and Braille) Guidelines for Shelters of GBV Survivors Developed
|  |  |  | Put in place and operationalise institutions & mechanisms mentioned in the Act for implementation (i.e Offenders register) | Statutory Bodies of the SODVA established and operationalised | Offices operational Human Resources and operational strategy for each statutory body Offender's register established | DPMO | MoJCA | 2024 - 2026 | DPMO & MoJCA Personnel
|  |  |  | Provide protection and comprehensive services for GBV survivors | GBV services (health, legal, pyschosocial support, and GBV shelter) | Number of one stop centres decentralised and operational | DPMO | Police, DPMO- Social Workers and psychologists/therapists, MoH - Clinicians, CSOs, development partners | 2024 | Costs of one stop centre per inkhundla
|  |  |  | Conduct continuous capacity building for duty bearers on the SODVA | Service providers are aware and are adhering to expectations as per their roles as spelt out in the SODVA | Number of trainings conducted for each cluster of service providers and the number of service providers reached (police, health workers, etc) | DPMO | Development partners, CSOs | 2024 - 2027 | Capacity enhancement trainings for service providers on GBV (480pp X 16 workshops X 25 people each session) | E192, 000
|  |  |  | Conduct public awareness campaigns targeted on the SODV Act including Gender Based Violence | Increased public awareness about the SODV Act and GBV | Number of sessions conducted and number of people reached | DPMO | Development partners, CSOs | 2024 | VOC, EBIS annual airtime payment, and CSO partners community outreach
Equality and Non-Discrimination
Service providers do not discriminate, exclude and treat all person's equally in their service delivery
Eq. + Non-D | 118.61,118.76, 118.164, 118.169, 118.173 - UPR | 20 & 21 ICCPR | To promote inclusivity ,diversity and equality of sexual and gender minorities | Conduct capacity building for frontline workers (Health care workers, Home Affairs, Correctional Services, and police officers amongst others) on Sexual Orientation, Gender Identity and Expression (SOGIE) | Capacity training sessions on SOGIE held | Number of service providers reached and sessions conducted | MoH, CHRPA | SNAP, Development partners, CSOs | 2024 - 2025 | (E480 X 25 people X 16 meetings ) one workshop for each sector per region | E192,000 | Sectoral Outcome 6.6 | SDG 3, 10, 16 | Constitution of the Kingdom of Eswatini (Section 20) SODV Act
Strengthening institutions for the promotion and protection of human rights
1. Strengthened, independent, and fully resourced National Human Rights Institution
2. A legally empowered, fully operational, and well resourced Legal Aid Office
| 118.46, 118.45, 118.48, 118.49, 118.51-118.56 - UPR 118.43 and 118.128 - UPR | UNCRC para 17, 71, ACERWC para 28, 52, CEDAW para 9, 13, 45 and 46, African Charter para 62, 79, ICCPR para 15, 41, Maputo Protocol para 81, 83 | Independent national Human Rights institution to comply with international human rights standards | Adopt enabling legislation compliant with Paris principles which guarantees financial independence of the Commission and restructuring | The Human Rights and Public Intergrity Commission has an independent budget | Independent Human Rights Commission restructured and strengthened | CHRPA | MoJCA | 2024 - 2025 | Personnel time |  | Sectoral outcome 4.2 and 7.3 | SDG 10 & 16 | Human Rights Bill Legal Aid Bill Amended Legal Practioners Act
ACCOUNTABILITY MECHANISMS |  |  |  | Strengthen human and financial resources of the Commission | Increased personnel and budget allocated to the Commission for programs | Increase in number of staff members of the Commisssion for programs and personnel Increased budget allocation | MoEPD/MoF | MoJCA/HRC | 2025 | Salaries for vacant posts Programmatic interventions funded
|  |  |  | Develop Strategic frameworks for the Commission | A guiding framework for the operations of the Commision | Strategic plan developed, accompanied by M& E Framework | HRC | MoJCA, Development Partners | 2024 | Consultancy Fees Consultative and validation meetings (E480 x 25 people X 2 meetings) | E150 000 E24 000 Consultative and validation meeting
|  |  | To enable access to justice for the indigent people | Finalize the Legal Aid Bill and amendment of Legal Practioners Act | Legal framework in place | Legal Aid Act and Amended Legal Practioners Act in place | MoJCA | Parliament and Legal Aid Office | 2024 - 2025 | MoJCA Personnel and Parliament Consultation meetings (E480X30X4 meetings) | E57 600.00
|  |  |  | Fully operationalise the Legal Aid Office | Legal Aid Office strengthened |  | MoJCA | MoF, Development partners | 2025 - 2026 | MoJCA Personnel
|  |  |  | Establish the Legal Aid Fund | An operation legal aid fund | Established mechanisms to access Fund Disaggregated data of Fund beneficiries (demographics and type of crime) | MoJCA | MoF, Development partners | 2026 - 2027 | Legal Aid Office Personnel time
Promotion and protection of the right to freedom of opinion, expression & access to information
1. Increased knowledge on fundamental rights and responsibilities amongst right holders and duty bearers
2. A conducive envirnment is provided through alignment of national laws with the Constitution of the Kingdom of Eswatini, and to international law
3. Platforms for national cohension are inclusive and accessible to all
CIVIL LIBERTIES | 118.98, 118.101, 118.105, 118.107, 118.111, 118.112, 118.220 - UPR 118.97, 118.102, 118.108, 118.110, 118.114, 118.222 - UPR | ICCPR para 36, 37, 44, and 45 African Charter para 64, 66 | Promote freedom of the press | Align laws with the Constitution to promote the rights to Freedom of the Press (finalize: The Access to Information Bill, Media Commission Bill,The Eswatini Broadcasting Bill) | National laws related to the press (Access to Information Bill, Media Commission Bill, Eswatini Broadcasting Bill) are enacted in conformity with the Constitution and international law | Access to Information Act, Media Commission Act, Eswatini Broadcasting Act passed in alignment with the Constitution | MoJCA | MoICT | 2024 - 2027 | MoJCA Personnel |  | Sectoral Outcome 7.4 | SDG 16 | Media Bills (i.e. Access to Information Bill, Media Commission Bill, Eswatini Broadcasting Bill
|  |  |  | Raise awareness to members of the public on rights and responsibilities | Members of the public able to balance their rights with those of others | Number of awareness raising sessions held, and number of ppeople reached | MoICT | CHRPA, Development Partners, and CSO partners | 2024 | VOC, EBIS, |  |  |  | Constitution of the Kingdom of Eswatini (Bill of Rights)
|  |  | Ensure the protection, respect and fulfilment of press freedom, and the rights and safety of journalists. | Strengthen and capacitate duty bearers, media personnel on the right to freedom of opinion, expression and access to information in relation to Eswatini legal frameworks and international law | Duty bearers and media personnel are capacitated on related civil liberties (freedom of opinion, expression, and access to information) | Number and sector of duty bearers reached Number of sessions held Number of journalists reached | MoICT | CHRPA, Development Partners, CSOs | 2024 | 2 sector trainings per region (E480 X 30 people X 8 meetings) | E115 000 |  |  | Media Commission Bill whose object is to promote and establish an equitable balance between the constitutional guarantees of freedom of the press and the protection and respect of the right to privacy is under review
|  |  |  | Adopt journalism good practices that operate with professional ethics and self-regulatory principles. | Adherence to journalism professional ethics and principles | Enactment and implementation of the Media Commission Bill Strengtherned media Obudsmen | MoICT | MoJCA, Media Houses in Eswatini, Journalists | 2024 - 2025 | MoICT Personnel |  |  |  | Eswatini Broadcasting Act no.7 of 2023
|  |  | To promote and protect public order in line with international law | Raise public awareness on the right to peaceful assembly in line with domestic and international law | Public is aware of their rights to peaceful assembly, and to enjoy it within the confines of the law | Number of participants reached Number of sessions held | MoLSS/MoJCA | HRC, Development partners, CSO Partners | 2024 | VOC, EBIS Airtime |  |  |  | Public Order Act no 12 of 2017, Constitution, Industrial Relations Act no.1 iof 2000, and The Code of Good Practice, Urban Government Act 1969
|  |  |  | Capacitate social partners agencies on management of public gatherings in line with relavant legislation | Social partner agencies (duty bearers) are capacitated in public order management in line with domestic and international law | Number of participants reached Number of sector agencies capacitated Number of sessions held | HRC | Development Partners, CSOs | 2024 | 2 meetings per region (E480 X 8 trainings X 30 people) | E115 000
Prohibition against Torture
1. Increased knowledge on fundamental rights, freedoms, and responsibilities
2. Strengtherned accountability mechanisms, and institutions to curb torture
TORTURE | 118.21, 118.79, 118.88 118.89 - UPR | 30 & 31 ICCPR ACHPR | To prevent and eradicate the use of torture and other cruel, inhuman and degrading treatment or punishment and ensuring accountability for acts of torture | Develop a clear procedure for receiving complaints of human rights violations | A procedural mechanism for reporting violations in place | Number of complaints made on torture, cruel, inhumane and degrading treatment | HRC | MoJCA/ICC | 2024 - 2025 | HRC Personnel (mainstream dissemination of complaints procedure into human rights sensitazation workshops) |  | Sectoral Outcome 10.1 | SDG 16.1 & 16.3 | Constitution of the Kingdomof Eswatini Police Act Correctional Services Act School Discipline Guidelines (MOET)
|  |  |  | Establish an Independent Complaints Commission to investigate allegations of torture or other ill-treatment which may be alleged against law enforcement agencies. | Independent Complaints Commission established | ICC gazzette Recruitment of ICC personnel | PMO | REPS, HMCS, UEDF and Development Partners | 2024 - 2026 | MoJCA Personnel
|  |  |  | Capacitate law enforcement officers on Human rights a) Review of training curriculum for newly recruited officers b) Conduct ToT for long serving officers on Human rights and dignity c) Conduct cascades training for long serving officials | Law enforcement officials syllabus reviewed to include human rights 4 X 20 regional ToT held 16 X30 workshops for law enforcement officials held | Revised training manual edition for law enforcement officials (recruits) 80 police official trainers' trained on human rights complaint policing 480 police officials trainined on human rights compliant policing | REPS, HMCS, UEDF | REPS, HMCS, UEDF | 2024 - 2026 | Reviewed Police Training Manual & printing TOT (E1900 pp accomodation and meals X 4 trainings x 20 people X 3 days) In service training (E480 X 16 meetings X 30 people) | E400 000 E456 000 E230 400
|  |  |  | Strengthening an accountability mechanism for perpetrators of torture and ill-treatment of public within the law enforcemnt agencies | Publicise reports and processing status of law enforcement officials reported for torture and ill-treatment of public | Number of cases processed and publicised | REPS, HMCS, UEDF | CHRPA, Law Enforcement Agencies, Sectoral Commissions of Police | 2024 - 2025 | Royal Eswatini Police Personnel
Ensuring favorable conditions of detention centres
1. Improved conditions of detention centres
2. Reduced overcrowding in prisons
DETENTION CENTRES | 118.94, 118.95 118.96 - UPR | 32, 33, and 34 ICCPR ACERWC para 54 ACHPR para 62, 65, CRC para 71, Maputo Protocol para 88 | To improve conditions of detention centres to ensure full enjoyment of rights by detainees | Strengthen the regular assessment of the conditions of detention centres in the country. | Regular detention centres public reports | Number of office bearers (official visitors & visiting Committee members) sensitised on their roles to assess detention centres conditions Number of visits and reports produced | His Majesty's Correctional Services | MoJCA, Development Partners | 2024 - 2025 | Staff Time |  |  | SDG 16 | Prisons Act 1964 His Majesty's Correctional Services Reports
|  |  |  | Revive the Criminal Justice Stakeholders forum to address challenges obtaining in detention centres | Criminal Justice Stakeholders Forum Meetings held | Quarterly meetings Reports or minutes of meetings | His Majesty's Correctional Services | MoJCA, Police, DPP, HMCS | 2024 - 2027 | Dedicated members of the Criminal Justice Stakeholder Forum (meeting refreshments) | E30 000 per annum
|  |  |  | Allocate necessary resources to renovate prisons and other detention centres | Refurbished detention centres and prisons | Number of detention centres and prisons renovated | MoF | MoF, MoJCA & MoPW&T | 2024 - 2027
|  |  |  | Explore other alternatives to imprisonment | Judicial officials trained on alternatives for imprisonment and alternatives implemented (i.e. juvenile justice administration) | Number of judicial officials trained on imprisonment alternatives Number of cases procesed through improsonment alternatives | His Majesty's Correctional Services | MoJCA, judiciary | 2024 - 2025 | Regional Trainings - Conference package and accomodation | E800 000
|  |  |  | Take measures to accommodate detainees with special needs | Detention centres rehabilitated to accommodate detainees with special needs | Qualitative and quantitativa data on rehabilitation of detention centres to suite PWDs | His Majesty's Correctional Services | MoJCA, HMCS, DPMO, & Development Partners | 2024 - 2025 | Assessment Report produced by HMCS
Ratification of and accession to International Instruments
1. Stakeholder consultations on the ratification Instruments
2. Deposition of Ratification, and or Accession Instruments
RATIFICATION | 118.11,118.12, 118.13,118.14, 118.15 - UPR |  | Ensure commitment to promote and protect human rights at International level | Ratify the Outstanding and Supported Instruments (OP CAT, OP CEDAW). | OP- CAT, OP CEDAW ratified | Optional protocols CAT & CEDAW ratified and the country interacts with the mechanisms | MoFAIC | MoFAIC | 2024 |  |  | Sectoral Outcome 7.3 | SDG 5 & 16 | State membership in the UN
|  |  |  | Engage stakeholders on their position with regards to the ratification of outstanding treaties | Stakeholder consultation report produced | Number of consultation meetings Number of participants reached | MoFAIC | MoJCA, MoFAIC | 2024 | MoFAIC
Compliance with treaty body reporting obligations
1. Submit overdue reports to treaty bodies
2. Develop a syatems and follow -up on the implementation of recommendations from human rights mechanisms
REPORTING | 118.33 - UPR |  | To comply with the country's reporting obligations | Strenghten NMRF Secretariat and Committee | Institutional strengtherning plan report produced and costed | Institutional strengthening plan implemented | MoJCA | MoJCA | 2024 | Institutional Capacity Assessment consultant | E150,000 | Sectoral Outcome 7.3 | SDG 16 | National Budget
|  |  |  | Develop and adopt a UPR Recommendations Implementation Plan | UPR implementetion plan developed | UPR Recommendation's plan implemented | NMRF | Interministrial | 2024
|  |  |  | Develop a NMRF Strategy | NMRF Stretegy developed | Strategic plan consultations report in place Implementation plan for strategy in palce | NMRF | MoJCA & Development Partners | 2024 | Consultancy Fees
|  |  |  | Establish an online recommendation tracking system | Online tracking system in place | Online tracking system in place | NMRF | MoJCA, Development Partners | 2027 | IT Consultancy Fees | E200 000
|  |  |  | Submit outstanding reports: Prioritize initial reports (CAT, ICESCR) and periodic reports | CAT & ICESCR state party reports developed | CAT & ICESCR submitted to the relevant UN mechanism | NMRF | MoJCA & MoFAIC | 2024 - 2025 | Consultation and validation meetings (4 meetings X E480 X 30 people) | E57 600

## M&E PLAN
MINISTRY RESPONSIBLE | ACTIVITY | INDICATORS | BASELINE | REFERENCES | TARGET | CURRENT VALUE | DATA SOURCE | FREQUENCY
Min of Economic Planning and Development | Conduct an analysis and mapping in the following variables (child poverty, working poor, and extreme poverty) | Poverty reduction % | Child pov. 56.5% Working poor 38.9% Extreme pov. 20.1% Poor 58.9% | Eswatini Household Income and Expenditure Survey, 2017 | 40% 34% 17% 54% |  | EHIES | ? Yearly
| Increase by 5% the budget allocation to poverty reduction programmes; and periodically review the implementation progress of the National Poverty Reduction Strategy Action Plan | Budget increase |  | Current total percentile allocation to Youth Development Fund, Rural Development Fund etc | 5% |  | Budget speech analysis report | Annually
DPMO | Revise and operationalise policies and guidelines on accessing adequate social protection grants and eliminate non-eligible recipients | Revised policy on social protection grants Receipient database updated | Social Protection Policy Draft 0 Sectorial disaggregated database |  | Social Protection Policy Social Protection Receipients Database |  | DPMO annual perfomance reports | 2025 Annually
| Conduct a robust resource mobilisation exercise under the health financing strategy to strengthen health care system. | Patients receive comprehensive health services, including access to all prescribed medication | 15% - 50% availability of essential drugs, and 2% for mental health drugs | https://www.hst.org.za/publications/NonHST%20Publications/Eswatini%20SARA%20March%20(05%2004%202019).pdf (page 21) | 80% availability of essential drugs, and 50% for mental health drugs |  | MoH Annual Report | Annually
| Increase awareness on social behaviour issues that inform development of NCDs, early detection and prompt treatment of non-communicable diseases like mental health, cancer, diabetes to name a few. | Number of people detected and treated for NCDs Number of people reached Number of sessions conducted | 0 |  | 13 000people /37% 600 000 people reached 24 sessions |  | Min of Health Annual Report & Media reach statistics | Monthly
| Conduct an assessment on comorbidity and cophamaceutical link to NCDs | Assessment report in place | 0 |  | A study Reports on Comorbidity and cophamaceutical link to NCDs |  | MoH Study Report
| Invest in the retention of skilled health providers within key departments of maternal and neonatal child health services | Skilled midwives ratio against annual births in each health centre | 0.96 Doctors per 10,000 population 41.42 nurses and midwives per 10,000 population | https://www.healthynewbornnetwork.org/hnn-content/uploads/2021-Countdown2030_Eswatini.pdf | 3 Doctors per 10,000 population ( was at 2.396 in 2018) 50 per 10,000 population (was at 40.555 in 2018) |  | WHO Data Indicator Details | Annually
| Invest in the availability and functionality of essential maternal neonatal child health equipment,drugs , and supplies in all level health facilities | Inventory report 15% of allocated budget allocated to equipment procurement | 0 invetory report 0% allocated to equipment |  | 1 national health equipment invetory report 15% of health allocated budget |  | MoH Invetory Report Health Budget Analysis Report | Once off Annually
| Increase SRH services to all adolescents for reduction in unintended pregnancies, exposure to STIs, increase use of contraceptives and treatment of infertility/sexual dysfunction. | % increase in SRH uptake by adolescents | 75% of 253 surveyed health centres provided family planning services Less than 5% provides for male or female sterilization | https://www.hst.org.za/publications/NonHST%20Publications/Eswatini%20SARA%20March%20(05%2004%202019).pdf | Investing in the availability of long-term reversible methods of family planning from 82% to 90% Increase FP Services in National Referral Hospitals given the high number of clients 0% reversible FP methods to 70% |  | MoH Annual Report | Annually
| Conduct community awareness and demand creation for good health seeking behaviours on key SRH services which includes early access to health facilities for pregnancy monitoring and child birth | Number of people reached Number of sessions conducted | 0 0 |  | 600 000 52 |  | Average Radio listernership Weekely/Bi-weekly media episodes by MoH | Monthly
| Strengthen the implementation of programmes to facilitate access to inclusive primary and secondary education, reduce repetition and increase retention address drop - outs etc. | Reduced % of drop outs from primary to high school Sustained % of enrolment from admission to completion, disaggregated in disability, OVCs, pregnant girls, ages, | Primary 92% Secondary Form 1 -3 78% Secondary Form 4 - 5 83% | Education Sector Strategic Plan 2022 - 2034 (page 116 - retention) | 94% 82% 87% (all targets for 2026) |  | ESSP Implementation Reports | Annually
| Improve enrolment rates by removing obstacles to access free primary education | Increased % in retention rate and completion rates (disaggregated by age, gender, disability) | 17% of 15 - 19 years out of school youths | ESSP | 13.5% in 2026 |  | Min of Education and Training Annual Reports | Annually
| Awareness raising workshops for school committees, headteachers Association, parents, and students on education policies i.e. related to pregnancy & retention | Reduced % of school drop outs as compared to previous years | X workshops conducted on ToT and cascade manner |  | 32 (School Committes and Headteachers) workshops annually (devide regions into subregions) |  | Min of Education and Training Annual Reports | Annually
| Increase access to adequate and safe/potable water, sanitation and hygiene | % increase of families with WASH operational infrastructure | 75.6% (EHIES,2017) 49% rural, informal, & peri-urban (EHIES) |  | 80% 65% |  | EHIES Min of Natural Resources Annual Reports | Annually
| Raise public awareness on practising appropriate and sustained hygiene behaviour | Number of people reached Number of sessions conducted | 0 0 |  | 600 000 people 24 sessions (twice a month) |  | MoH Annual Reports | Annually
| Increase water sources through the construction of at least 2 new multi - purpose dams | 2 multi-purpose dams constructed | 0 |  | 2 dams |  | Min of Natural Resources Reports | Annually
| Review Water Act 2003 to strengthen the governance of water supply in the country | Water Act addresses governance of water supply |  |  | Passed Amendment Act |  | Min of Natural Resources Reports | Annually
| Raise awareness on issues affecting stateless persons | Number of sessions conducted Number of people reached | 0 |  | 500000 |  | Min of Home Affairs Annual Report | Annually
| Conduct study on stateless people in Eswatini | Statelessness report | 0 |  | Disaggregated data on statelessness |  | Statelessness Research Report | Once off
| Continue to roll out the mop-up exercise to Manzini and Hhohho Regions | Number of persons reached during mop-up drive in Manzini and Hhohho regions | 0 |  | (To be informed by study report) |  | Mop-up birth registration database | Annually
| Enforce the implementation (Section 10 (1) (2)(3) of the Births Marriages and Deaths Act to achieve universal birth registration (MoU between MOHA&MOH), to address registration of children born out of wedlock | New births registered before hospital discharge upon birth by 2026 | 24.181 births per 1000 people (2023 birth rate) |  | 100% registered at birth |  | Birth Registration database disagregated in age, sex, marital status, and region | Bi-annually
| Speed up operationalisation of the Civil Registration law to increase access for stateless people in Eswatini to acquire citizenship | Gradual elimination of statelessness | 0% |  | 80% (based on stateleness study report |  | Birth Registration database disagregated in age, sex, marital status, and region | Bi-annually
| Conduct awareness raising on the rights and welfare of PWDs especially Persons with Albinism | Number of sessions held Number of people reached | 0 0 |  | 24 500 000 |  | DPMO Narrative Reports, & Media appearances | Quarterly
| Fully operationalise the PWD Act of 2018 | Statutory bodies for PWDs appointed and operational | Number of statutory bodies as per PWD ACT |  | All statutory bodies are in place and operational |  | DPMO - Annual Reports | Annually
| Provide support to increase access to education with appropriate learning materials, assistive devices and trained educators. | Number of persons with albinism provided with appropriate education, assistive devices Number of educators trained. Proportion of Inclusive Schools in Eswatini | 0 0 |  | 50% |  | DPMO & Min. of Education and Training Annual Reports | Annually
| Provide health care accessories for persons with Albinism | Number of PWAs accessing health care accessories | 0
| Provide legal assistance for PWDs | Proportion of PWDs accessing legal assistance disaggregated by rights violated, sex, age, type of disability | 0 |  | X % of the total number of legal assistance services rendered |  | MoJCA Legal Aid Report | Annually
| Establish a registry for PWDs, including PWA | Number of PWDs captured into the registry; disaggregate by sex, age, diability, and service received) | 176 184 PWDs in Eswatini 101 722 women 74 462 men | 2017 Population and Housing Census Preliminary report | All PWDs are entered into the Registry, and its is annually updated |  | Registry at DPMO with Disaggregated Data (electronic copy) | Annually
| Identify and mobilize marginalised groups to participate in the development and implementation platforms of climate change and disaster | Total number of each of the marginalised groups participating in climate change and DRR meetings | 0 |  | 20% PWDs participation rate |  | Attendance Registers | All Meetings
| Prioritization of vulnerable groups in responding to rescue operations of climate change and disaster risk. | Rescue mission plans shows prioratization of vulnerable groups (i.e. PWDs, elderly and children); and all disasters accounted for | 0 on the NDMA National Multi-Hazard Contigency Plan 2019 - 2020, 0 on IFRC Network Country Plan (2023)Baphalali Eswatini |  | Vulnerable groups prioritized on national rescue operations |  | NDMA Reports | Annually, and after a disaster
| Strengthen the early warning systems to integrate the vulnerable groups as well as populations at risk | Qualitative and quantitative reports | Inclusion of vulnerable groups in early warning systems |  | Vulnerable groups are included in early warning systems |  | NDMA Plans and Mission Reports | Perfomance Reviewed Annually or after each disaster
| Produce and disseminate a simplified version of the SODVA in accessible formats | Number of knowledge products produced per format, dissemination records on audience reached (i.e. location, mode of communication, demographics of audience) | 1 English and Siswati simplified version of the SODVA (FHI 360) 10 752 Siswati version Copies | UNFPA Annual Report 2021 | Simplified versions of the SODVA, including Braille, Drama, additional print outs in SiSwati and English, community engagements |  | DPMO Annual Reports on the Activity | Annually
| Put in place and operationalise institutions & mechanisms mentioned in the Act for implementation (i.e Offenders register, | Offices & operational strategy for each body Human resources Offenders Register in place
| Provide protection and comprehensive services for GBV survivors | Number of one stop centres decentralised and operational | 3 (Mbabane Government Hospital, RFM & Lubombo Referral Hospital) | 50 Million Women Speak, WomenConnect - Social Services in Eswatini | 8 (2 per region, upper and lower region) |  | MoH Annual Reports | Annually
| Conduct continuous capacity building for duty bearers on the SODVA | Number of trainings conducted for each cluster of service providers and the number of service providers reached (police, health workers, etc) | Police, health workers, Judicial officials |  | 400 Annually (proportional representation) |  | DPMO Annual Report | Annually
| Conduct public awareness campaigns targeted on the SODV Act including Gender Based Violence | Number of sessions conducted and number of people reached | 0 0 |  | 24 sessions (bi-monthly) 600 000 people reached |  | DPMO | Annually
| To promote inclusivity ,diversity and equality of sexual and gender minority | Number of service providers reached per sector, and sessions conducted | 0 |  | 400 service providers reached |  | MoH and CHR&PI Annual/Activity Reports | Annually
| Strengthen human and financial resources of the Commission | Number of additional staff employed & % budget allocation compared to previous years | Has experienced staff turn-over recently
| Develop Strategic frameworks for the Commission | Strategic plan developed, accompanied by M& E Framework | None |  | A strategic & operational plan, with M&E Plan in place |  | Commission on Human Rights and Public Administration Report | 2026
| Adopt enabling legislation compliant with Paris principles which guarantees financial independence of the Commission and restructuring | Legislative framework adopted | Draft Bill |  | An Act operationalising the CHR&PI Act |  | CHRPA Annual Reports | 2025
| Establish the Legal Aid Fund | Number of people assisted through fund | 0 |  | To be determined |  | Legal Aid Office Annual Reports | Annually
| Finalize the Legal Aid Bill | Legal Aid Bill enacted into law by 2025 | Legal Aid Bill |  | Legal Aid Act by 2025 |  | MoJCA Annual Report | 2025
| Operationalise the Legal Aid Office | Amended Legal Practioners Act & number of people assisted by office annually | 0 |  | Amended Legal Practioner's Act by 2025 X People offered legal services |  | Legal Aid Office Annual Reports | 2025 Annually
| Align laws with the Constitution to promote the rights to Freedom of the Press (finalize: The Access to Information Bill, Media Commission Bill,The Eswatini Broadcasting Bill) | Access to Information, Media Commission Bill, and Eswatini Broadcasting Bill passed into law | Access to Information Bill, Media Commission Bill, and Eswatini Broadcasting Bill |  | Access to Information, Media Commission Bill and Eswatini Braodcasting Bill enacted into law and implemented |  | Min Of ICT Annual Report | Annually (2024 - 2027)
| Raise awareness to members of the public on rights and responsibilities | Number of sessions conducted Number of people reached | 0 0 |  | 52 sessions 600 000 people |  | CHR&PI Annual reports Public Media | Annually
| Strengthen and capacitate duty bearers, media personnel on the right to freedom of opinion, expression and access to information in relation to Eswatini legal frameworks and international law | Number and sector of duty bearers reached Number of sessions held Number of journalists reached
| Adopt journalism good practices that operate with professional ethics and self-regulatory principles. | Enacted and implemention of the Media Commission Bill Market the media ombudsmen | Media Commission Bill None |  | Media Commission Act by 2025 Public adverts of media ombudsmen |  | Min. of ICT Annual report Public Media | Once off Daily for 6 months
| Raise public awareness on the right to peaceful assembly in line with domestic and international law | Number of sessions held Number of people reached | 0 0 |  | 52 (one per week) 600 000 people |  | Ministrial Annual Reports | Weekely
| Capacitate social partners agencies on management of public gatherings in line with relavant legislation | Number of participants per sector Number of sessions held | 0 0 |  | 240 trained sector agencies 8 sessions |  | Commission on Human Rights & Public Integrity Report | Quarterly
| Develop a clear procedure for receiving complaints of human rights violations | Number of cases received, processed, and publicised | 0 |  | 500 cases publicised |  | Commission on Human Rights & Public Integrity | Annually
| Establish an Independent Complaints Commission to investigate allegations of torture or other ill-treatment which may be alleged against law enforcement agencies. | ICC gazzetted and operationalised ICC resourced | No gazzette 0% Budget allocation for the ICC |  | ICC Gazetted and operational by 2026 Personnel and Operational budget allocation |  | Progress Report | Annually
| Capacitate law enforcement officers on Human rights a) Review curriculum for new recruits b) Conduct ToT for in-service c) Conduct in-service training for serving police officials | a) Reviewed training material b) 80 Police Officials attended TOT c) 480 in service trained officials | a)Training manual unreviewed b) 0 trained TOT Police Officials c) 0 trained in service officials |  | a) Reviewed training manual b) 80 Police Officials undergone ToT c) 480 in service trained police officials |  | Progress Reports | a) Once off b)Once off c) Annually
| Strengthening an accountability mechanism for perpetrators of torture and ill-treatment of public within the law enforcemnt agencies | Number of cases received, processed, and publicised | 12 (2 police officials charged with homicide in relation to death of a detanee (in 2015); 3 officials invistigated for torture by the Commuion on Human Rights; 1 man awarded E70K following an assualt by UEDF in 2003; 5 community police of Sihhohweni arrested for assualt; and 1 UEDF member charged for xenophobic attacks of a Mozambican national |  | All reported cases processed and published within reasonable time |  | REPS, HMCS, UEDF Reports on Torture | Annually
| Strengthen the regular assessment of the conditions of detention centres in the country. | number of stakeholders visiting (by institution) Number of visits and reports produced | HRC and listed officials as per Act (official visitors and visiting committees) 0 | Correctional Services Act | All Instituions No. of reports from all listed institutions |  | Institutional websites, and media interviews | Annually
| Revive the Criminal Justice Stakeholders forum to address challenges obtaining in detention centres | Number of meetings held Issue based reports and minutes | 0 0 |  | 4 meetings 4 minutes/reports |  | HMCS Annual Report | Quarterly
| Allocate necessary resources to renovate prisons and other detention centres | Number of renovated centres, and project reports
| Explore other alternatives to imprisonment | Number of judicial officials trained on imprisonment alternatives Number of cases procesed through improsonment alternatives (juvenile and adults) | 0 245 persons in pre-trail detention for 12 or more months | Commission on Human Rights and Public Integrity , March 2018 survey | 120 judicial official trained 150 cases processed through alternatives to imprisonment |  | MoJCA Annual Report | Annually
| Take measures to accommodate detainees with special needs | Qualitative and quantitativa data on rehabilitation of detention centres to suite PWDs | None |  |  |  | HMCS Annual Report | Annually
| Ratify the Outstanding and Supported Instruments (OP CAT, OP CEDAW. | Optional protocols CAT & CEDAW ratified | 0 |  | 2 Instruments |  | UN Human Rights Country Ratification status | 2024-2025
| Conduct Consultations towards the Convention on the Prevention and Punishment of the Crime of Genocide | Number of consultation meetings (stakeholder or locations) Number of people reached | 0 0
| Strenghten NMRF Secretariat and Committee | Institutional strengthening plan implemented i.e. New gazatte for Committtee | Term of Office for Committee members | Internal Consultations Report | Adopt a new Gazette (consider sustainability, replacements, and continuity) |  | NMRF/MoJCA Annual Report | 2024
| Develop and adopt a UPR Recommendations Implementation Plan | UPR Plan implememted (review meetings reports) | None | NMRF Activity Schedule | UPR Implementation Plan |  | NMRF Annual Report | 2024-05-01
| Develop a NMRF Strategy | Implementation strategy in place | None | NMRF Activity Schedule | 2024 - 2029 NMRF Strategic Plan |  | NMRF Annual Report
| Establish an online recommendation tracking system | Online tracking system updated quarterly | None | NMRF Activity schedule | Operational tracking system |  | NMRF Website | After adoption of Recommendations; and update annually
| Submit periodic and all outstanding reports, prioritize initial reports (CAT, ICESCR) | CAT & ICESCR submitted | 9 (8 initial reports, and 1 periodic report) | NMRF Reporting Schedule | 2 |  | https://tbinternet.ohchr.org UN Treaty Body Databse | Once in 2024/2025
Note on B51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is the Fund not serving the same purpose as the legal aid office?
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For best practices, see UNHCR Emergency Handbook - Guidelines on Preparedness Section
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WHO, Eswatini - Risk of Premature Deaths due to NCDs (%_
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.who.int/data/gho/data/indicators/indicator-details/GHO/medical-doctors-(per-10-000-population) 2018 is the recent highest - fluctuating health demands affects the ratio
Note on F11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: National Referrals provided only male and female condoms, and male and female sterilization as per the report referenced