Bilharzia Programme

The core mandate for the Bilharzia programme is to control morbidity with de-worming for the schistosomiasis and soil transmitted helminthiasis.

Achievements:

The increase in the public demand for deworming services manifest by the number of public that collect tablets for the control of worm infection which escalates every year from 59,198 in 2011 to 74,551 in 2012.

The year 2009, of the suspension of school deworming came with public understanding of the importance of de-worming through alertness at the re-emerging of symptoms that were cleared during the routine school-aged children deworming service era in schools – families are nowadays collecting increased numbers of Albendazole as seen in the above report.

Table 2.6: Annual Action Plan for Bilharzia

| Strategic Objective (SO 3A): National Bilharzia & Intestinal Worm Control: To improve provision of and increase access to essential, affordable and quality public health services in order to reduce Bilharzia and Intestinal Worm disease burden, morbidity and mortality and improve the health status of the population at risk. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicator | Activity | Baseline end Jan-Dec 2012 |  |  | 3rd Quarterly Performance (Oct-Dec, 2012) Quarterly report |  |  | Target end – April 2013 to April 2014 Annual Work-plan |  |  |
| % clients treated for Bilharzia (Bilha) and intestinal worms or(STH) soil-transmitted Helminth in the laboratory(Lab) & HF. | # of cases treated for Bilharzia and STH in the Lab and in all Health facilities-(HF). | Bilharzia: a)Lab. clients = 1108 b) HF.pts = 5560 STH: a) Lab. clients = 85200 b) HF.pts = 22530 |  |  | Bilharzia: a)Lab. Clients = 209 b)HF. Pts= 1311 STH: a) Lab. Clients = 18635 b) HF. Pts = 598 |  |  | Bilharzia: a) Lab. Clients = 1500 b) HF. Pts= 6400 STH: a)Lab. Clients = 100000 b) HF. Pts =23000 |  |  |
| % routine control cases for high risk groups: Preschool - (pre SAC), (PW)-pregnant women, (SAC)-school aged children, (CDD)-community drug distribution | # of cases from high risk groups (GRP) on routine control for intestinal worms(STH)-Soil-transmitted Helminth and Bilharzia (Bilha) | GRP Pre SAC PW SAC CDD | STH 95320 21305 16863 612 | Bilha * * 8066 * | GRP Pre SAC PW SAC CDD | STH 22320 3260 3363 204 | Bilha * * 3362 * | GRP Pre SAC PW SAC CDD | STH 100000 25000 300000 200000 | Bilha * * 150000 200000 |
| % stakeholders trained in deworming IEC | # Of Trained stakeholders in the routine control and prevention of worm infections. | 793Healthmotivators forCDD 300 Health workers 139 pre-school Teachers 100 School Teachers |  |  | 150 Health Motivators 21 Health workers 10 pre-school teachers 13 School teachers |  |  | 800 Health Motivators 350 Health Workers 150 pre-school teachers 80 teachers |  |  |

Challenges:

One of the challenges the the programme faces is the reliance on the inadequate government funds to carry out its activities. Shortages of funds have resulted in delays in school deworming restoration services of stakeholders’ trainings and logistics preparation.