## Cover-BackCover
Swaziland
Country Accountability Framework
A tool for assessing and planning implementation of the country accountability framework for health with a focus on women's and children's health
2012-09-18
Purpose
1. | To provide an overview of the current status of the different components of a country accountability framework, with a focus on MNCH
2. | To lay the foundation for the development of a roadmap with specific activities to implement the country accountability framework
3. | To serve as a general monitoring tool to track progress towards implementing the priority activities and accountability framework implementation
Action
Monitor
 Review

## Country context
Swaziland
Information updated: INSERT DATE
Global strategy on women and children / commitment (PNMCH)
National Health Sector Plan | Duration | Key priority areas/relevant information | Key funding partners
National RMNCH Plan (and other relevant progammatic plans - cMYP (immunization), HIV, malaria, etc.) | Duration | Key priority areas/relevant information | Key funding partners
Key donors/partners investing in accountability activities | Approximate funding amount | Key priority areas funded/relevant information | Key funding partners
CRVS
Monitoring of Results
Information Communication Technology
MDSR
National review mechanisms
Resource tracking
Advocacy
Calendar of major upcoming events/activities (e.g., national health sector reviews, programmatic reviews, Countdown events, national COIA workshop, IHP+ related events, grant development-related workshops (e.g., for GAVI or the Global Fund), etc.) | Dates | Key stakeholders involved/relevant information
Country team present at the multi-country Accountability Workshop

## CRVS
| ASSESSMENT | Civil registration and vital statistics systems (CRVS) | 33.33% |  |  | Swaziland
Score: (1) Not present, needs to be developed; (2) Needs a lot of strengthening; (3) Needs some strengthening ; (4) Already present, no action needed
A | Civil registration and vital statistics systems (CRVS) | Situation analysis (strengths, weaknesses/gaps) | Score |  |  | Possible Actions
1 | ASSESSMENT & PLAN |  | 1.5 | 1.5 | 1.5
a | A rapid assessment of the status and practices of CRVS has been conducted in the last 5 years | 1a. Partly done (pilot, not covering whole country). MICS 2010 has captured registration of births only but no other vital statistics 1b. Not done | 2 | 2 |  | Use the UNICEF report as a basis for future improvements. Implement assessment tool. Advocate for strengthening of the existing CVRS program.
b | A full assessment of the status and practices of CRVS has been conducted and a improvement plan has been developed |  | 1 | 1 |  | Recommend and advocate holistic for assessment. Strengthen data collection and storage system. Strengthen quality assurance procedures.
Enforce regulations that oblige reporting of vital events (births and deaths) in medical establishments/ institutions to the Statistics unit.
Create public awareness on the importance of vital registration especially the vulnerable groups. training and refresher courses for registrars
2 | COORDINATING MECHANISM |  | 2 | 2 | 2
a | There is an interagency coordinating committee that involves key stakeholders from civil registrar's office, national statistics office, ministry of health etc. | There is formal committee, but needs to actively coordinate activities (Revival of the HISCC) | 2 | 2 |  | Strengthen interagency coordinating committee involving all key stakeholders
Revival and motivation of HISCC
3 | HOSPITAL REPORTING |  | 3 | 3 | 3
a | Hospital reporting of deaths is complete and accurate | Reporting of death to the central government system not possible due to lack of connectivity. Death certificates are in many hospitals not possible to print. Still using ICD9 for reporting at hospitals but MD10 has the ICD10 form at the back. Staff for reporting is needed. | 3 | 3 |  | Hospitals need network points, computers and printers to produce certificates and report deaths.
b | Hospital reporting of deaths includes a cause of death, using the ICD-10, with regular quality control |  | 3 | 3 |  | Training of doctors in ICD 10; regular quality control of certification; improve coding practices
Encourage private clinics to use ICD 10 for reporting, especially private sector
Proper channel of reporting maternal deaths needs to be strengthened as some clinicians are not aware where to report. Recruit or identify staff for reporting.
4 | COMMUNITY REPORTING |  | 2.5 | 2.5 | 2.5
a | Community births and deaths are reported, using ICT where appropriate, covering the whole country | 4a. Registered at some constituencies, late registration of births and deaths. Often registered at the constituency level, but not taken further to the central government. ICT for reporting is gradually being introduced. The BMD Act is under review, draft will be ready by December. 4b. VA is done for deaths without medical certification. Two mobile registration trucks are going out to the communities/chiefdoms. The government is decentralising the registration services. | 2 | 2 |  | Strengthen community reporting of births and deaths, implement innovative approaches (involve RHM and SRH community focal person). Amend current BMD Act. Revise existing community based health information tool.
b | Verbal autopsy (VA) is done for deaths without medical certification in the community |  | 3 | 3 |  | Strengthen community reporting through use of VA by chiefdom representatives (runners). Start using reporting forms to be used by chiefdoms
5 | VITAL STATISTICS |  | 1 | 1 | 1
a | Vital statistics (fertility and mortality) are published every year, for national and subnational level, with data quality assessment | Vital statistics not published every year. | 1 | 1 |  | Modify existing quality assessment tool to the structures in Swaziland. Published vital statistics every year.
6 | LOCAL STUDIES FOR MORTALITY STATISTICS (HDSS) |  | #DIV/0! |  | 0
|  |  |  | 0 |  | Strengthen and expand the HDSS system
Create public awareness on reporting to EPR

## Monitoring Results
| ASSESSMENT | Monitoring of results | 50% |  |  | Swaziland
Score: (1)Not present, needs to be developed; (2) Needs a lot of strengthening; (3) Needs some strengthening ; (4) Already present, no action needed
B | Monitoring of results | Situation analysis (strengths, weaknesses/gaps) |  |  |  | Possible Actions
1 | M&E PLAN |  | 2 | 2 | 2
a | There is a comprehensive M&E plan for the National Health Strategy that specifies indicators, data sources, analysis, dissemination and roles and responsibilities | 1.a No, there are several fragmented M&E program plans but the country is in the process of developing a comprehensive plan for health in line with the revised NHSSP 1.b The integrated SRH plan has not been finalised since we were waiting for the MTR of the SRH strategic plan to be completed. The ministry has reviewed the NHSSP and the recommendations have not been incorporated into the just reviewed SRH strategy | 1 |  |  | 1.Support the development of the comprehensive M&E Plan for health according to the revised NHSSP; by conducting three workshops (consensus, validation and dissemination) with the relevant stakeholders. Conduct orientation of Health care workers on compilation of data using the M&E plan
b | The RMNCH M&E plan is fully aligned with the overall health sector M&E plan and includes the 11 core RMNCH indicators |  | 3 |  |  | 2.Finalize the SRH strategic plan and incorporate the NHSSP MTR recommendations into the integrated SRH strategy document including the M&E plan:- Conduct 2 workshops to finalise the SRH strategy and M&E plan
3
2 | M&E COORDINATION |  | 3 | 3 | 3
a | There is a well-functioning national M&E coordination committee, with representation of the key constituencies (MOH, statistics, academia, civil society, development partners, UN) | There is a formalised coordination committee meant to meet quarterly with TORs in place There is a formalised coordination committee meant to meet quarterly with TORs in place There is a formalised coordination committee meant to meet quarterly with TORs in place There is a formalised coordination committee meant to meet quarterly with TORs in place | 3 |  |  | A well-functioning national M&E coordination committee needs stakeholders full commitment to meet regularly: Meeting regularly convened by the M&E manager(Meeting costs for 4 meetings annually)
3 | HEALTH SURVEYS |  | 1 | 1 | 1
a | There is a national household health survey plan | 3. a.No plan yet. CSO is currently focusing on MICS 2013/14 3.b.No | 1 |  |  | Work with CSO to ensure that indicators for women's and children's health interventions are included in the survey tools: conduct meetings / workshops with CSO to review tools.
b | A MNCH intervention coverage survey is planned for 2012-2013 |  | 1
4 | FACILITY DATA (HMIS) |  | 3.5 | 3.5 | 3.5
a | There is a well functioning facility reporting system (HMIS) that provides subnational statistics for core indicators, with a data quality report | 4.aYes 4.b Verification done quarterly and indicators are selected as needed. However for maternal deaths reporting and verification is very weak. Service availability mapping done in 2012/13. Service availability and readiness assessment (SARA) needs to be done to assess quality of care and create a baseline for lifesaving commodities. | 4 |  |  | Strengthen the capacity of health care workers on data quality , conduct 4 regional training workshops for health care workers
b | A facility survey for data verification and service readiness is carried out annually |  | 3 |  |  | Strengthen data audits and validation. Conduct facility data audit and validation
Establish data verification on maternal and neonatal deaths reporting (work with MDSR and IDSR) by establish a national/ regional/facility/community verification core teams/focal persons
Conduct a SARA
5 | ANALYTICAL CAPACITY |  | 2 | 2 | 2
a | Good quality analytical reports of progress and performance are produced to inform reviews (annual, mid term, final) | 5. Other reports have been done but never for SRH/MNCH | 2 |  |  | Strengthen analytical capacity for the SRH/MNCH indicators and produce annual reports; conduct data analytical trainings for identified focal persons from M&E/ SRH national/ regional and facilities
6 | EQUITY |  | 3 | 3 | 3
a | Disaggregated health data on key indicators (sex, income, minority and location) are used extensively in reviews | 6. SDHS, and MICS, VAC data is aggregated on income and expenditure , sex , location and age | 3 |  |  | Work with CSO to ensure that indicators for women's and children's health interventions and analytical equity are included.
7 | DATA SHARING |  | 3 | 3 | 3
a | There is an up-to-date country health data repository, including subnational data, for public access to all relevant reports and data on key health indicators | The ministry does have a repository and HMIS. however there is no proper dissemination plan as there is no resource center for every one to access | 3 |  |  | a. Strengthen national data repository with all relevant data and reports, i) establish hard copies resource centers for health at national/ regional/ health facilities. Ii) make the electronic data source more comprehensive and more accessible
b. Make summarised reports in siswati and disseminate to communities annually.

## MDSR
| ASSESSMENT | Maternal death surveillance and response | 50% |  |  | Swaziland
Score: (1) Not present, needs to be developed; (2) Needs a lot of strengthening; (3) Needs some strengthening ; (4) Already present, no action needed
C | Maternal death surveillance and response | Situation analysis (strengths, weaknesses/gaps) | Score |  |  | Possible Actions
1 | NOTIFICATION: |  | 4 | 4 | 4
a | There is a national policy requiring notification of all maternal deaths (maternal death is a notifiable event within 24 hours) | yes, maternal deaths are reported within 24 hours through EPR . | 4
2 | CAPACITY TO REVIEW AND ACT |  | 3 | 3 | 3
a | There is national capacity to review and act as part of a system of maternal death surveillance and response | 2.a confidential enquiry committee in place 2.b.There are National & Regional MDR committees in place and they also exist in some health facilities. There is a need to include neonatal death audits within MDR | 3 | 3 |  | Strengthen national capacity through training in MDSR including neonatal death audits ICD1 0
b | There is district capacity to review and act as part of a system of maternal death surveillance and response |  | 3 |  |  | The four regional committees have just been recently constituted there is need for capacity building through training in MDSR and ICD 10
Integrate MNDSR with IDSR in notification and surveillance
3 | HOSPITALS/FACILITIES |  | 2 | 2 | 2
a | Hospital reporting of maternal deaths is nearly complete (over 90%) and timely (within 24 hours) and provides reliable cause of death using ICD | 3.a reporting is not timely and not reliable as the country still uses the ICD 9 coding 3.b most maternal deaths occurring at facility are reviewed both at private and public but the challenge is submission of the notification forms | 2 |  |  | Provide supportive supervision & mentoring of HCW on MDSR, Train providers on the guidelines, Conduct National & Regional data meeting to share best practices to motivate HCWs Improve reporting by hospitals; Training in ICD 10 coding certification and coding (links with CRVS)
b | All maternal deaths occurring in hospitals (public and private) are reviewed |  | 2 |  |  | Strengthen hospital capacity and practices, including private sector in reviewing all maternal and neonatal deaths
4 | QUALITY OF CARE |  | 3 | 3 | 3
a | Quality of care assessments are conducted in a sample of maternity facilities on a regular basis (at least once every two years) | A situation analysis on improving the quality of maternal and neonatal health services was conducted once in 2010, however due to lack of funds it will not be done this year | 3 |  |  | Mobilize funds to conduct quality of care assessment
Conduct quality of care assessment in maternity care facilities
5 | COMMUNITY REPORTING & FEEDBACK |  | 2 | 2 | 2
a | All community maternal deaths are reported to districts within 24 hours | 5.a not all maternal deaths at community level are reported within 24 hours. however a focal person for every chiefdom has been identified and oriented on need of notification of maternal and neonatal deaths in all the regions. 5.b yes a toll free line is used by community focal persons to report to national level 5.c In the process of finalizing the Community VA forms. 5.d does not exist | 3 |  |  | Conduct supportive supervision and mentoring for the focal persons at chiefdom level. Create awareness at community level to report all maternal and neonatal deaths within 24hrs to the responsible persons at national level (contacts given). Can use existing 977 system.
b | Electronic devices are used to get faster and more complete reporting from communities and to initiate response |  | 2 |  |  | Strengthen the existing system of maternal and neonatal deaths reporting and initiation of response by electronic devices.
c | Verbal autopsies are done for community maternal deaths |  | 2 |  |  | Finalize the VA forms and train the SRH regional mentors to conduct VAs on maternal and neonatal deaths in communities.
d | Communities receive feedback and are involved in the review |  | 1 |  |  | Develop a system of involving communities in verbal autopsies and response
6 | REVIEW OF THE SYSTEM: |  | 1 | 1 | 1
| The maternal death surveillance and response system is reviewed annually in terms of completeness of surveillance and quality of the response, including actions to improve quality of care | no done triennially | 1 |  |  | Initiate and institutionalize annual review of surveillance and response system for maternal and new born deaths including timely dissemination and use of the report

## eHealth
| ASSESSMENT | Innovation and eHealth | 27.78% |  |  | Swaziland
Score: (1) Not present, needs to be developed; (2) Needs a lot of strengthening; (3) Needs some strengthening ; (4) Already present, no action needed
D | Innovation and eHealth | Situation analysis (strengths, weaknesses/gaps) | Score |  |  | Possible Actions
1 | POLICY |  | 1 | 1 | 1
a | A national eHealth strategy or policy has been developed, including the use of ICT for MNCH | There is no national eHealth strategy and policy developed. | 1 |  |  | To develop eHealth Policy and Strategy
Incorporate MNCH in the policy that is to be developed
2 | INFRASTRUCTURE |  | 2 | 2 | 2
a | There is connectivity (Internet, broadband, and mobile) and infrastracture (computers) available for health reporting in urban areas, district capitals and rural areas | Not all hospitals, public health units, private hospitals, and health centres are connected and have ICT infrastructure. Community based health volunteers do not access to communication gadgets to report to the emergency task force. | 2 |  |  | Determine desired targets and priorities for infrastructure deployment to support health services delivery and information flows.
Strengthen and scale up of connectivity and infrastructure and Community based health volunteers to have access to connectivity gadgets to communicate to the emergency task force.
Capacity building for users including the community care volunteers
3 | SERVICES |  | 2 | 2 | 2
a | eHealth services and applications are used to improve recording, reporting and performance of information systems (e.g., reporting on maternal death or immunization) | There is data sharing at the regional level and some facilities have ehealth but most facilities use a paper-based system. | 2 |  | 0 | Determine the eHealth services required to support the country’s priority programs and goals, particularly with respect to information flows.
b | There is effective data sharing between systems (e.g. facility data on child health workload with health worker information) | Regions have feedback sessions to facilities by making powerpoint presentations on the performance of facilities | 2 |  |  | Reporting system needs to be strengthened by providing mentoring and supportive supervision to the facilities
Scale up data sharing through the use of government website by giving access to programmes to upload reports.
4 | STANDARDS |  | 3 | 3 | 3
| There are commonly agreed interoperability requirements or standards for eHealth services and application, e.g for data storing, transfer and compilation | There are commonly agreed interoperability requirements for data storing, transfer and compilation, but these standards are not formally documented | 3 | 3 |  | Document and disseminate the existing Health Information systems standards and interoperability components required to support eHealth services, applications and infrastructure, as well as to support broader changes to health information flows.
Review the HIS standards and guidelines to meet the current technology trend
5 | GOVERNANCE |  | 1 | 1 | 1
| There is a national coordination mechanism for eHealth, with stakeholder involvement (health and non-health) in planning and implementation. | The national coordination mechanism for eHealth is under development. There is an Egovernment Steering Committee which will have to coordinate all egovernment activities. | 1 |  |  | Finalise the establishment and support of a strong effective eHealth coordination mechanism. Establish a national steering group for eHealth, supported by a project team with planning skills and knowledge of eHealth. Assess which organizations or groups are active in eHealth, and their potential role in the development of a national eHealth program.
6 | PROTECTION |  | 2 | 2 | 2
a | Data protection, legislation and regulatory frameworks exist for sharing health information. | Data protection exits but there is no legislation in place to protect data. | 2 |  |  | Develop data protection policies and guidelines. Assure health sector, ministerial and government leadership and support. Ensure that the required program development skills and expertise are available.
b | Data protection policies are enforced and adhered to | The available data protection guidelines are adhered to. | 2 |  |  | Enforce compliance to data protection policies

## Monitoring resources
| ASSESSMENT | Monitoring of resources | 6.667% |  |  | Swaziland
Score: (1) Not present, needs to be developed; (2) Needs a lot of strengthening; (3) Needs some strengthening ; (4) Already present, no action needed
| Monitoring of resources | Situation analysis (strengths, weaknesses/gaps) | Score |  |  | Possible Actions
a | There is an officially approved NHA framework built upon international guidelines (SHA 2011 key + beneficiaries classifications for tracking RMNCH flows) | There is an international NHA framework but the country has not yet been customized to local context. There is no formal governance mechanism that specifies coordination, management, national indicators and budget for implementing health accounts and tracking resources on key policy issues | 1 |  |  | Adopt the revised NHA framework (SHA 2011)
b | There is a formal governance mechanism that specifies coordination, management, national indicators and budget for implementing health accounts and tracking resources on key policy issues such as financial flows for RMNCH |  | 1 |  |  | Establish the NHA subgroup as part of the Health financing TWG, with TORs for producing NHA on an annual basis
Sensitize high level ministry and other relevant stakeholder ministry officials on the the NHA Framework
2 | COMPACT |  | 2 | 2 | 2
a | There is a formal agreement (or compact) between government and partners that requires reporting on partner commitments and disbursements, and donor funded expenditures on health (including on flows for RMNCH) | There is a sector-wide approach (SWAp) in place, but requires strengthening. | 2 |  |  | Organize a meeting to engage government and development partners and work towards a "compact" which requires all development partners, NGOs and other stakeholders in the health sector to report data on health expenditures and results regularly and in a standarised format.
3 | COORDINATION |  | 1 | 1 | 1
a | There is an NHA steering committee that provides technical oversight on data needs, methods of production and data use | There is no NHA steering committee that provides technical oversight. Key stakeholders are not actively involved in the production of the NHA | 1 |  |  | Set up the NHA steering committee as a sub-group of the Health Financing TWG, with officially approved TORs, with institutional support, and functioning using results-based management methods
b | Key stakeholders are actively involved in the production of NHA (including government stakeholders at national and subnational level, CSOs, NGOS, partners, health insurance companies) |  | 1 |  |  | Ensure inclusion of all key stakeholders in resource tracking /NHA
4 | PRODUCTION |  | 1 | 1 | 1
a | There is adequate human capacity at national and subnational levels to produce NHA tables and core indicators, including on expenditure by beneficiaries for tracking flows on RMNCH | Human capacity to produce NHA at national and regional levels is inadequate. There is no government expenditure data conversion into the NHA format. There is no central database for the automated production of standard NHA tables | 1 |  |  | Train NHA TWG on national health accounts 2011.
b | Government expenditure data conversion into NHA format is automated, including for expenditure by beneficiaries |  | 1 |  |  | Map government codes to NHA codes and develop IT conversion tool for NHA
c | There is a central database for automated production of standard NHA tables, including tables by beneficiaries; automated production of key indicators (including COIA indicators); methods and sources are well documented and accessible |  | 1 |  |  | Develop database for production of NHA
5 | ANALYSIS |  | 1 | 1 | 1
a | Analytical summaries are produced annually on NHA 2011 health accounts (including beneficiaries) | Analytical summaries of the NHA 2011 are not produced annually. The NHA 2011, indicators and analyses are not publicly accessible | 1 |  |  | Produce the NHA report and analytical summaries
b | NHA 2011 (including beneficiaries for tracking RMNCH) and indicators and analyses are publicly accessible |  | 1 |  |  | Disseminate report and analyses and avail them on public website
6 | DATA USE |  | 1 | 1 | 1
a | NHA 2011 (including beneficiaries for tracking RMNCH) are an essential element of annual reviews and are used in the development of national policies, including RMNCH-specific policies | NHA 2011 are not an essential element of annual reviews and are not used in the development of national policies | 1 |  |  | Facilitate the use of NHA data in the policy making process

## Review processes
| ASSESSMENT | Review processes | 50% |  |  | Swaziland
Score: (1) Not present, needs to be developed; (2) Needs a lot of strengthening; (3) Needs some strengthening ; (4) Already present, no action needed
| Review processes | Situation analysis (strengths, weaknesses/gaps) | Score |  |  | Possible Actions
1 | REVIEWS |  | 2 | 2 | 2
a | Multi-stakeholder review meetings are conducted every year to review health sector performance against annual and long term goals and targets | Annual reviews are not conducted; however, a mid-term-review of the National Health Sector Strategic Plan was conducted in 2012. Key stakeholders have limited involvement in the preparation and execution of the reviews. RMNCH reviews are conducted irregularly at individual program level not at multi-stakeholder level. | 2 |  |  | Undertake systematic multi-stakeholder annual reviews in line with goals, targets of the NHS and other national and global development priorities. Establish an independent monitoring and peer review mechanism to enhance validation and documentation of best practices
b | Key stakeholders are actively involved in the preparation and execution of the reviews (MOH, other sectors, academia, development partners, UN, private sector and civil society including women's organizations, ) |  | 2 |  |  | Create a forum at national level for multi-stakeholder active participation and define processes, timelines and accountability mechanism to ensure better quality of the annual and periodic reviews
c | RMNCH programme reviews are held annually and aligned with the national health sector review |  | 2 |  |  | Based on Annual Plans, develop a calendar to ensure that the RMNCH reviews are held as planned and findings are disseminated and used to inform programming and decision making.
2 | SYNTHESIS OF INFORMATION AND POLICY CONTEXT |  | 2 | 2 | 2
a | The health sector performance reviews are informed by a good synthesis of all relevant health data, including RMNCH, with sub national analyses | Health sector performance reviews mainly informed by synthesis of relevant data from health facilities | 2 |  |  | Develop and implement in health training institutions, a training curriculum for health workers on health data management, M&E and reviews
b | The reviews are informed by a systematic analysis of qualitative data , e.g. policy changes, public opinion, service provider opinions |  | 2 | b |  | Train key health sector personnel in data collection, collation, synthesis, analysis and interpretation for production of quality reports.
Develop and implement guiding principles and policies for comprehensive data collection and use beyond health facilities
3 | FROM REVIEW TO PLANNING |  | 3 | 3 | 3
a | There are mechanisms in place to translate results of the review meeting into planning processes and resource allocation decisions at all levels | Mechanisms to translate results of the review meeting into planning processes exist only at the national and regional levels at limited scale. There is active participation of key stakeholders in the annual operational planning meetings but not all stakeholders participate | 3 |  |  | Establish a Task Team that oversees reviews and implementation of review findings and recommendations for planning purposes and informed decision making at all levels
b | Annual operational planning meetings have active participation of all key stakeholders |  | 3 |  |  | Enforce participation of all stakeholders in the annual reviews.
4 | COMPACTS OR SIMILAR MECHANISMS |  | 3 | 3 | 3
a | There is a country compact or similar mechanism (a government-led process of planning, coordination and facilitation of all development partners, including funding flows) and adherence is good | There is health sector partner coordination in the implementation of the national health sector strategic plan. Development partners are committed to the country "compact." However, Adherence is limited and coordination with some gaps | 3 |  |  | Develop an agreement framework for coordination of partners and implementation of the National Health Sector Establish a functional partner coordination Unit to lead planning, coordination and facilitation of all Development partners
b | All major development partners are committed to the country "compact", aim to align their resource allications and adjust their budget allocation according to country review & planning outcomes |  | 3 |  |  | Put in place effective systems and protocols for partner coordination to implement the health strategic plan

## Advocacy & outreach
| ASSESSMENT | Advocacy and outreach | 19.44% |  |  | Swaziland
Score: (1) Not present, needs to be developed; (2) Needs a lot of strengthening; (3) Needs some strengthening ; (4) Already present, no action needed
| Advocacy & outreach | Situation analysis (strengths, weaknesses/gaps) | Score |  |  | Possible Actions
1 | PARLIAMENT ACTIVE ON RMNCH ISSUES |  | 1.5 | 1.5 | 1.5
a | Parliament has established transparent accountability mechanism for RMNCH, such as a multi-stakeholder commission or committee that reports to parliament. | There is a multi-stakeholder committee (IATCC) but it does not report to parliament. There are no public forums for information sharing | 2 |  |  | Advocate for appointment of a focal person from parliament health portfolio committee for RMNCH issues. Develop a strong and effective information exchange mechanisms between the IATCC and the health portfolio committee
b | Parliament organizes public forums for information sharing and discussions on RMNCH issues |  | 1 |  |  | Establish forums for public hearings and information sharing on RMNCH. Sensitize Parliamentarians on RHMNCH issues through Health Portfolio Committee
2 | CIVIL SOCIETY COALITION |  | 2.5 | 2.5 | 2.5
a | Civil society coalitions exist, are funded, and meet regularly with key stakeholders, including government, parliamentarians, multi-sectoral policy/decision-making body, and media | The SRH Civil Society Task Force affiliated to CANGO has been formed and officially launched in 2013. Civil Society Task Force meets regularly to share information, plan and review progress and attends the IATCC. Currently there is no forum to meet parliament. The Task Force is in the process of mobilizing resources and developing a strategic plan to inform coordinated planning, advocacy, implementation of activities, sharing of results and information and peer review | 3 |  |  | Establish forum for Task Force to interact with Parliament. Establish a functional office for the Task Force. Develop, implement and monitor Task Force Strategic plan
b | Civil Society coalition(s) produce evidence-based advocacy messages and materials with effective dissemination strategy |  | 2 | 2 |  | Train Civil Society SRH Task Force for effective coordination and advocacy through results-based approach.
3 | MEDIA ROLE | Situation analysis (strengths, weaknesses/gaps) | 1.3333 | 1.3333 | 1.3333
a | There is frequent and robust media reporting on a wide range of RMNCH-related topics, including policy and budget action | Media reporting exits but the focus is not solely on RMNCH issues. The media's accountability processes are not clearly defined. Media does not receive regular information and briefings from key national bodies to generate reports and public discussion debate | 2 |  |  | Conduct workshops and meetings for the media on accurate, responsive and responsible reporting on RMNCH related issues
b | Media are actively engaged in the accountability process, reporting on progress towards implementation of the national commitments towards the Global Strategy |  | 1 |  |  | Work with the media to report on the monitoring and implementation of the Global Strategy
c | Media receive information and briefings from key national bodies (e.g. annual reviews) to generate reports and public discussion/debate |  | 1 |  |  | Plan and conduct meeting with media to improve information flow.
4 | COUNTDOWN EVENT FOR RMNCH |  | 1 | 1 | 1
a | At least one national Countdown event for RMNCH is held during 2012-2014, presenting available information on RMNCH and involving high-level decision makers (e.g. parliamentarians), government, civil society, media and other stakeholders | The parliament is aware of the Countdown event and will support it. National updates are conducted on MDGs and other strategic goals that includes RMNCH. | 1 | 1 |  | Conduct count down activities/agenda such as RMNCH annual conference/indaba for advocacy, public awareness, and updates
b | A country CountDown report or profile is produced and is of high quality |  | 1 |  |  | Prepare Countdown report / profile updates that are evidence based.

## Summary scores
Accountability framework | Swaziland
Summary scores of self assessment
February 2012
Civil registration and vital statistics systems (CRVS) | 33.33%
Monitoring of results | 50%
Maternal death surveillance and response | 50%
Innovation and eHealth | 27.78%
Monitoring of resources | 6.667%
Review processes | 50%
Advocacy & outreach | 19.44%

## Assessment report
COUNTRY ACCOUNTABILITY FRAMEWORK: Scorecard |  |  |  |  | Swaziland
KEY:
1 | Not present, needs to be developed
2 | Needs a lot of strengthening
3 | Needs some strengthening
4 | Already present/no action needed
Civil registration & vital statistics systems |  |  |  | Situation analysis (strengths, weaknesses/gaps) | Priority actions
Assessment & Plan |  | 1.5 |  | 1a. Partly done (pilot, not covering whole country). MICS 2010 has captured registration of births only but no other vital statistics 1b. Not done . There is formal committee, but needs to actively coordinate activities (Revival of the HISCC). Reporting of death to the central government system not possible due to lack of connectivity. Death certificates are in many hospitals not possible to print. Still using ICD9 for reporting at hospitals but MD10 has the ICD10 form at the back. Staff for reporting is needed. . 4a. Registered at some constituencies, late registration of births and deaths. Often registered at the constituency level, but not taken further to the central government. ICT for reporting is gradually being introduced. The BMD Act is under review, draft will be ready by December. 4b. VA is done for deaths without medical certification. Two mobile registration trucks are going out to the communities/chiefdoms. The government is decentralising the registration services. . Vital statistics not published every year.. | Use the UNICEF report as a basis for future improvements. Implement assessment tool. Advocate for strengthening of the existing CVRS program.
Coordinating Mechanism |  | 2 |  |  | Strengthen interagency coordinating committee involving all key stakeholders
Hospital reporting |  | 3 |  |  | Hospitals need network points, computers and printers to produce certificates and report deaths.
Training of doctors in ICD 10; regular quality control of certification; improve coding practices
Encourage private clinics to use ICD 10 for reporting, especially private sector
Community reporting |  | 2.5 |  |  | Strengthen community reporting of births and deaths, implement innovative approaches (involve RHM and SRH community focal person). Amend current BMD Act. Revise existing community based health information tool.
Strengthen community reporting through use of VA by chiefdom representatives (runners). Start using reporting forms to be used by chiefdoms
Vital statistics |  | 1 |  |  | Modify existing quality assessment tool to the structures in Swaziland. Published vital statistics every year.
Local studies for mortality |  | #DIV/0! |  |  | Strengthen and expand the HDSS system
Create public awareness on reporting to EPR
60
Monitoring of results |  |  |  | Situation analysis (strengths, weaknesses/gaps) | Possible actions
M&E Plan |  | 2 |  | 1.a No, there are several fragmented M&E program plans but the country is in the process of developing a comprehensive plan for health in line with the revised NHSSP 1.b The integrated SRH plan has not been finalised since we were waiting for the MTR of the SRH strategic plan to be completed. The ministry has reviewed the NHSSP and the recommendations have not been incorporated into the just reviewed SRH strategy . There is a formalised coordination committee meant to meet quarterly with TORs in place There is a formalised coordination committee meant to meet quarterly with TORs in place There is a formalised coordination committee meant to meet quarterly with TORs in place There is a formalised coordination committee meant to meet quarterly with TORs in place. 3. a.No plan yet. CSO is currently focusing on MICS 2013/14 3.b.No.4.aYes 4.b Verification done quarterly and indicators are selected as needed. However for maternal deaths reporting and verification is very weak. Service availability mapping done in 2012/13. Service availability and readiness assessment (SARA) needs to be done to assess quality of care and create a baseline for lifesaving commodities. .5. Other reports have been done but never for SRH/MNCH.6. SDHS, and MICS, VAC data is aggregated on income and expenditure , sex , location and age .The ministry does have a repository and HMIS. however there is no proper dissemination plan as there is no resource center for every one to access . | 1.Support the development of the comprehensive M&E Plan for health according to the revised NHSSP; by conducting three workshops (consensus, validation and dissemination) with the relevant stakeholders. Conduct orientation of Health care workers on compilation of data using the M&E plan
2.Finalize the SRH strategic plan and incorporate the NHSSP MTR recommendations into the integrated SRH strategy document including the M&E plan:- Conduct 2 workshops to finalise the SRH strategy and M&E plan
M&E Coordination |  | 3 |  |  | A well-functioning national M&E coordination committee needs stakeholders full commitment to meet regularly: Meeting regularly convened by the M&E manager(Meeting costs for 4 meetings annually)
Health Surveys |  | 1 |  |  | Work with CSO to ensure that indicators for women's and children's health interventions are included in the survey tools: conduct meetings / workshops with CSO to review tools.
0
0
Facility data (HMIS) |  | 3.5 |  |  | Strengthen the capacity of health care workers on data quality , conduct 4 regional training workshops for health care workers
Strengthen data audits and validation. Conduct facility data audit and validation
Analytical capacity |  | 2 |  |  | Strengthen analytical capacity for the SRH/MNCH indicators and produce annual reports; conduct data analytical trainings for identified focal persons from M&E/ SRH national/ regional and facilities
Equity |  | 3 |  |  | Work with CSO to ensure that indicators for women's and children's health interventions and analytical equity are included.
Data sharing |  | 3 |  |  | a. Strengthen national data repository with all relevant data and reports, i) establish hard copies resource centers for health at national/ regional/ health facilities. Ii) make the electronic data source more comprehensive and more accessible
Maternal death surveillance & response |  |  |  | Situation analysis (strengths, weaknesses/gaps) | Possible actions
Notification |  | 4 |  | yes, maternal deaths are reported within 24 hours through EPR . . 2.a confidential enquiry committee in place 2.b.There are National & Regional MDR committees in place and they also exist in some health facilities. There is a need to include neonatal death audits within MDR. 3.a reporting is not timely and not reliable as the country still uses the ICD 9 coding 3.b most maternal deaths occurring at facility are reviewed both at private and public but the challenge is submission of the notification forms. A situation analysis on improving the quality of maternal and neonatal health services was conducted once in 2010, however due to lack of funds it will not be done this year. 5.a not all maternal deaths at community level are reported within 24 hours. however a focal person for every chiefdom has been identified and oriented on need of notification of maternal and neonatal deaths in all the regions. 5.b yes a toll free line is used by community focal persons to report to national level 5.c In the process of finalizing the Community VA forms. 5.d does not exist. no done triennially.
Capacity to review and act |  | 3 |  |  | Strengthen national capacity through training in MDSR including neonatal death audits ICD1 0
The four regional committees have just been recently constituted there is need for capacity building through training in MDSR and ICD 10
Hospitals / facilities |  | 2 |  |  | Provide supportive supervision & mentoring of HCW on MDSR, Train providers on the guidelines, Conduct National & Regional data meeting to share best practices to motivate HCWs Improve reporting by hospitals; Training in ICD 10 coding certification and coding (links with CRVS)
Strengthen hospital capacity and practices, including private sector in reviewing all maternal and neonatal deaths
Quality of care |  | 3 |  |  | Mobilize funds to conduct quality of care assessment
Community reporting & feedback |  | 2 |  |  | Conduct supportive supervision and mentoring for the focal persons at chiefdom level. Create awareness at community level to report all maternal and neonatal deaths within 24hrs to the responsible persons at national level (contacts given). Can use existing 977 system.
Strengthen the existing system of maternal and neonatal deaths reporting and initiation of response by electronic devices.
Finalize the VA forms and train the SRH regional mentors to conduct VAs on maternal and neonatal deaths in communities.
Develop a system of involving communities in verbal autopsies and response
Review of the system |  | 1 |  |  | Initiate and institutionalize annual review of surveillance and response system for maternal and new born deaths including timely dissemination and use of the report
Innovation and eHealth |  |  |  | Situation analysis (strengths, weaknesses/gaps) | Possible actions
Policy |  | 1 |  | There is no national eHealth strategy and policy developed. . Not all hospitals, public health units, private hospitals, and health centres are connected and have ICT infrastructure. Community based health volunteers do not access to communication gadgets to report to the emergency task force.. There is data sharing at the regional level and some facilities have ehealth but most facilities use a paper-based system. . There are commonly agreed interoperability requirements for data storing, transfer and compilation, but these standards are not formally documented. The national coordination mechanism for eHealth is under development. There is an Egovernment Steering Committee which will have to coordinate all egovernment activities.. Data protection exits but there is no legislation in place to protect data. . | To develop eHealth Policy and Strategy
Incorporate MNCH in the policy that is to be developed
Infrastructure |  | 2 |  |  | Determine desired targets and priorities for infrastructure deployment to support health services delivery and information flows.
Strengthen and scale up of connectivity and infrastructure and Community based health volunteers to have access to connectivity gadgets to communicate to the emergency task force.
Capacity building for users including the community care volunteers
Services |  | 2 |  |  | Determine the eHealth services required to support the country’s priority programs and goals, particularly with respect to information flows.
Reporting system needs to be strengthened by providing mentoring and supportive supervision to the facilities
Scale up data sharing through the use of government website by giving access to programmes to upload reports.
Standards |  | 3 |  |  | Document and disseminate the existing Health Information systems standards and interoperability components required to support eHealth services, applications and infrastructure, as well as to support broader changes to health information flows.
Governance |  | 1 |  |  | Finalise the establishment and support of a strong effective eHealth coordination mechanism. Establish a national steering group for eHealth, supported by a project team with planning skills and knowledge of eHealth. Assess which organizations or groups are active in eHealth, and their potential role in the development of a national eHealth program.
Protection |  | 2 |  |  | Develop data protection policies and guidelines. Assure health sector, ministerial and government leadership and support. Ensure that the required program development skills and expertise are available.
Enforce compliance to data protection policies
Monitoring of resources |  |  |  | Situation analysis (strengths, weaknesses/gaps) | Possible actions
National health accounts |  | 0 |  | There is an international NHA framework but the country has not yet been customized to local context. There is no formal governance mechanism that specifies coordination, management, national indicators and budget for implementing health accounts and tracking resources on key policy issues . There is a sector-wide approach (SWAp) in place, but requires strengthening.. There is no NHA steering committee that provides technical oversight. Key stakeholders are not actively involved in the production of the NHA . Human capacity to produce NHA at national and regional levels is inadequate. There is no government expenditure data conversion into the NHA format. There is no central database for the automated production of standard NHA tables . Analytical summaries of the NHA 2011 are not produced annually. The NHA 2011, indicators and analyses are not publicly accessible . NHA 2011 are not an essential element of annual reviews and are not used in the development of national policies . | Adopt the revised NHA framework (SHA 2011)
Establish the NHA subgroup as part of the Health financing TWG, with TORs for producing NHA on an annual basis
Compact |  | 2 |  |  | Organize a meeting to engage government and development partners and work towards a "compact" which requires all development partners, NGOs and other stakeholders in the health sector to report data on health expenditures and results regularly and in a standarised format.
Coordination |  | 1 |  |  | Set up the NHA steering committee as a sub-group of the Health Financing TWG, with officially approved TORs, with institutional support, and functioning using results-based management methods
Ensure inclusion of all key stakeholders in resource tracking /NHA
Production |  | 1 |  |  | Train NHA TWG on national health accounts 2011.
Map government codes to NHA codes and develop IT conversion tool for NHA
Develop database for production of NHA
Analysis |  | 1 |  |  | Produce the NHA report and analytical summaries
Disseminate report and analyses and avail them on public website
Data Use |  | 1 |  |  | Facilitate the use of NHA data in the policy making process
Review processes |  |  |  | Situation analysis (strengths, weaknesses/gaps) | Possible actions
Reviews |  | 2 |  | Annual reviews are not conducted; however, a mid-term-review of the National Health Sector Strategic Plan was conducted in 2012. Key stakeholders have limited involvement in the preparation and execution of the reviews. RMNCH reviews are conducted irregularly at individual program level not at multi-stakeholder level. . Health sector performance reviews mainly informed by synthesis of relevant data from health facilities. Mechanisms to translate results of the review meeting into planning processes exist only at the national and regional levels at limited scale. There is active participation of key stakeholders in the annual operational planning meetings but not all stakeholders participate. There is health sector partner coordination in the implementation of the national health sector strategic plan. Development partners are committed to the country "compact." However, Adherence is limited and coordination with some gaps. | Undertake systematic multi-stakeholder annual reviews in line with goals, targets of the NHS and other national and global development priorities. Establish an independent monitoring and peer review mechanism to enhance validation and documentation of best practices
Create a forum at national level for multi-stakeholder active participation and define processes, timelines and accountability mechanism to ensure better quality of the annual and periodic reviews
Based on Annual Plans, develop a calendar to ensure that the RMNCH reviews are held as planned and findings are disseminated and used to inform programming and decision making.
Synthesis of information & policy context |  | 2 |  |  | Develop and implement in health training institutions, a training curriculum for health workers on health data management, M&E and reviews
Train key health sector personnel in data collection, collation, synthesis, analysis and interpretation for production of quality reports.
Develop and implement guiding principles and policies for comprehensive data collection and use beyond health facilities
From review to planning |  | 3 |  |  | Establish a Task Team that oversees reviews and implementation of review findings and recommendations for planning purposes and informed decision making at all levels
Enforce participation of all stakeholders in the annual reviews.
Compacts or equivalent mechanisms |  | 3 |  |  | Develop an agreement framework for coordination of partners and implementation of the National Health Sector Establish a functional partner coordination Unit to lead planning, coordination and facilitation of all Development partners
Put in place effective systems and protocols for partner coordination to implement the health strategic plan
Advocacy & outreach |  |  |  | Situation analysis (strengths, weaknesses/gaps) | Possible actions
Parliament active on RMNCH issues |  | 1.5 |  | There is a multi-stakeholder committee (IATCC) but it does not report to parliament. There are no public forums for information sharing . The SRH Civil Society Task Force affiliated to CANGO has been formed and officially launched in 2013. Civil Society Task Force meets regularly to share information, plan and review progress and attends the IATCC. Currently there is no forum to meet parliament. The Task Force is in the process of mobilizing resources and developing a strategic plan to inform coordinated planning, advocacy, implementation of activities, sharing of results and information and peer review . Media reporting exits but the focus is not solely on RMNCH issues. The media's accountability processes are not clearly defined. Media does not receive regular information and briefings from key national bodies to generate reports and public discussion debate . The parliament is aware of the Countdown event and will support it. National updates are conducted on MDGs and other strategic goals that includes RMNCH.. | Advocate for appointment of a focal person from parliament health portfolio committee for RMNCH issues. Develop a strong and effective information exchange mechanisms between the IATCC and the health portfolio committee
Establish forums for public hearings and information sharing on RMNCH. Sensitize Parliamentarians on RHMNCH issues through Health Portfolio Committee
Civil Society Coalition |  | 2.5 |  |  | Establish forum for Task Force to interact with Parliament. Establish a functional office for the Task Force. Develop, implement and monitor Task Force Strategic plan
Train Civil Society SRH Task Force for effective coordination and advocacy through results-based approach.
Media role |  | 1.3333 |  |  | Conduct workshops and meetings for the media on accurate, responsive and responsible reporting on RMNCH related issues
Work with the media to report on the monitoring and implementation of the Global Strategy
Plan and conduct meeting with media to improve information flow.
Countdown event for RMNCH |  | 1 |  |  | Conduct count down activities/agenda such as RMNCH annual conference/indaba for advocacy, public awareness, and updates
Prepare Countdown report / profile updates that are evidence based.

## Summary Roadmap
| SUMMARY ROADMAP | [10 empty] | Swaziland
|  |  |  | Responsibility |  | Year of implementation (Indicate with x)
Score | Actions (replaced as required) | Priority (1=v high, 2=high, 3=medium 4=low) | Suggested approach/methods (replace as required) | Lead govt/ national institute | Partners |  | 2013 | 2014 | 2015 | Total Estimated Cost per action | 2012/13 Catalytic funding (total max. amount $250k) | Unfunded balance | Potential sources for funding unmet balance | Approach/methods
33.33% | CIVIL REGISTRATION AND VITAL STATISTICS SYSTEMS (CRVS)
2 | Use the UNICEF report as a basis for future improvements. Implement assessment tool. Advocate for strengthening of the existing CVRS program. | 3 | develop tools for the rapid assessment to include deaths and marriages | Ministry of Home Affairs, DPM's Office | UNICEF, PEPFAR, UNDP, WHO |  |  | X |  | 5000 | 5000 | 0 |  | Organize national stake holders meeting, apply rapid assessment tool
1 | Recommend and advocate holistic for assessment. Strengthen data collection and storage system. Strengthen quality assurance procedures. | 2 | Apply full assessment tool and develop improvement plan | Ministry of Home Affairs, DPM's Office | UNICEF, PEPFAR, UNDP |  |  | X |  | 50000 | 10000 | 40000 |  | Apply full assessment tool and develop improvement plan
| Enforce regulations that oblige reporting of vital events (births and deaths) in medical establishments/ institutions to the Statistics unit. | 1 | Part of the process of revising the BMD Act. | MHA, DPM'O,MOH | UNICEF, PEPFAR, UNDP |  |  | X |  | 1500 |  | 0
| Create public awareness on the importance of vital registration especially the vulnerable groups. training and refresher courses for registrars | 2 | Cooperate with the media and the chiefdoms | MHA, DPM'O, MOH, Legislators | UNICEF, PEPFAR, UNDP |  | X |  |  | 20000 |  | 0
2 | Strengthen interagency coordinating committee involving all key stakeholders | 1 | Multi-stakeholder workshop /mobilisation exercise |  |  |  | x |  |  | 0 |  | 0 |  | Multi-stakeholder workshop /mobilisation exercise
| Revival and motivation of HISCC | 1 | as above | CSO, MOH, MHA | WHO, UNDP |  | X |  |  | 0 |  | 0
0
3 | Hospitals need network points, computers and printers to produce certificates and report deaths. | 2 | Investing in HIS infrastructure (Cost estimate does not include human resources) | MOH, CSO | WHO, |  |  | X |  | 50000 | 10000 | 40000 |  | Invest in strengthening HMIS
3 | Training of doctors in ICD 10; regular quality control of certification; improve coding practices | 3 | train and capacitate doctors and relevant staff on the use of ICD10 | MOH | WHO, UNFPA |  |  | X |  | 10000 |  | 0 |  | Train national facilitators, apply electronic tools
| Encourage private clinics to use ICD 10 for reporting, especially private sector | 2 | as above | MOH | WHO, UNFPA |  |  | X |  | 5000 |  | 0
| Proper channel of reporting maternal deaths needs to be strengthened as some clinicians are not aware where to report. Recruit or identify staff for reporting. | 1 | Strengthen orientation and induction of newly employed personnel. | MOH | EGPAF, ICAP, WHO, UNFPA |  | X |  |  |  |  | 0
2 | Strengthen community reporting of births and deaths, implement innovative approaches (involve RHM and SRH community focal person). Amend current BMD Act. Revise existing community based health information tool. | 1 | Identify short list of variables for birth and death reporting (HMN/WHO) | MOH, MHA, DPM'O | WV, |  |  | X |  | 20000 |  |  | Supported by UNICEF | Identify short list of variables for birth and death reporting (HMN/WHO)
3 | Strengthen community reporting through use of VA by chiefdom representative (runners). Start making reporting forms to be used by chiefdoms | 1 | Test verbal autopsy tool for mobile phones | MOH, DPM'O, MHA | WV, |  |  | X |  | 5000 |  | 5000 |  | Test verbal autopsy tool for mobile phones
0
0
1 | Modify existing quality assessment tool to the structures in Swaziland. Published vital statistics every year. |  | M&E unit modifies the tool. The CSO produces vital statics annually. Training as necessary. | MOH | WHO, UNAIDS, UNICEF, UNDP |  |  | X |  | 30000 |  | 30000 |  | Training in analyses of relevant staff
0
0
3 | Strengthen and expand the HDSS system |  | Assess and invest in HDSS | MOH, | WHO, UNFPA, |  |  | X |  | 10000 |  | 10000 |  | Assess and invest in HDSS
| Create public awareness on reporting to EPR |  | Collaborate with the media to educate the public. | MOH, | WHO, UNFPA, FLAS |  | X |  |  | 2000 |  | 2000
0
50% | MONITORING OF RESULTS
1 | 1.Support the development of the comprehensive M&E Plan for health according to the revised NHSSP; by conducting three workshops (consensus, validation and dissemination) with the relevant stakeholders. Conduct orientation of Health care workers on compilation of data using the M&E plan | 1 | Conduct three workshops (consensus, validation and dissemination) with the relevant stakeholders these will be 4 days workshops for 30 people partially residential. Conduct orientation of Health care workers on collection, compilation and use of data using the M&E plan. These will be 5 days workshops of theory and practices for 30 health workers per session ( 1 workshop for each region (4 )) | MOH | UN partners, PEPFAR and USG partners, World Bank, |  | X | X |  | 106866.7 | 20000 |  |  | Review M&E component, revise according to WHO/IHP+ guidance
2 | 2.Finalize the SRH strategic plan and incorporate the NHSSP MTR recommendations into the integrated SRH strategy document including the M&E plan:- Conduct 2 workshops to finalise the SRH strategy and M&E plan | 1 | Conduct 2 , 3 day workshops for 30 people to finalise the SRH strategy and M&E plan | MOH | UN partners, PEPFAR and USG partners, World Bank, |  | x | X |  | $12,233 |  | 12233 |  | Workshop with key stakeholders
1 | #REF! | 1 |  |  |  |  | X |  |  |  |  | 0
1 | 3 | 1 |  |  |  |  | x | X |  |  |  | 0
3 | A well-functioning national M&E coordination committee needs stakeholders full commitment to meet regularly: Meeting regularly convened by the M&E manager(Meeting costs for 4 meetings annually) | 1 | Conduct 4 meetings annually for 40 people per session | MOH | UN partners, PEPFAR and USG partners, World Bank, |  | X |  |  | $3377 | $1000 | 2377 |  | Link with National Statistical Plan, mapping all health surveys
| #REF! | [10 empty] | 0
| #REF! | [10 empty] | 0
1 | Work with CSO to ensure that indicators for women's and children's health interventions are included in the survey tools: conduct meetings / workshops with CSO to review tools. | 2 | Conduct 4 meetings with CSO . Conduct (20pple) | MOH | MOH and supporting partners |  |  | X |  | $400 | $0 | 400 |  | Liaise with MICS, DHS, raise funding, determine contents
1 | [7 empty] | X |  |  |  | 0 |  | Use WHO analytical approach including data quality score card analysis
| #REF! | [10 empty] | 0
| #REF! | [10 empty] | 0
4 | [11 empty] | 0 |  | TA and training on analyses and development of annual stastical report
3 | Strengthen data audits and validation. Conduct facility data audit and validation. Establish data verification on maternal and neonatal deaths reporting (work with MDSR and IDSR) by establishing a national/ regional/facility/community verification core teams/focal persons. | 2 | Conduct facility data audit exercise annually. | MOH | UN partners, PEPFAR and USG partners, World Bank, |  | X | X | X | $4,600 | $0 | 4600 |  | Plan sample survey of facility (about 100) prior to review using WHO standard instrument
| Conduct verification annually.Establish data verification on maternal and neonatal deaths reporting (work with MDSR and IDSR) by establish a national/ regional/facility/community verification core teams/focal persons. Conduct a SARA to monitor the quality of services and monitor the availability of life-saving commodities at facility level. | 1 | Establish verification teams at national and regional annually. Procure vehicles for verification teams. Conduct the SARA (USD 100 000) TA | MOH | UN partners, PEPFAR and USG partners, World Bank, |  |  | X |  | $170,000 | 50000 | 120000
| #REF! | [10 empty] | 0
2 | Strengthen analytical capacity for the SRH/MNCH indicators and produce annual reports; conduct data analytical trainings for identified focal persons from M&E/ SRH national/ regional and facilities | 1 | Conduct 4 days workshops for 30 people for analytical data training partially residential. 1 workshop for each region TA | MOH | UN partners, PEPFAR and USG partners, World Bank, |  | X | X | X | $81,555 | $ |  |  | Build upon current national and regional observatory approaches, WHO analysis and data quality tools
| #REF! | [10 empty] | 0
| #REF! | [10 empty] | 0
3 | Work with CSO to ensure that indicators for women's and children's health interventions and analytical equity are included. | 2 | Conduct 2 days' workshop with CSO to include Equity and SRH indicators | MOH | UN partners, PEPFAR and USG partners, World Bank, |  | X | X | X | $200 |  | 200 |  | Technical assistance and training onequity analyses
| #REF! | [10 empty] | 0
| #REF! | [10 empty] | 0
3 | a. Strengthen national data repository with all relevant data and reports, i) establish hard copies resource centers for health at national/ regional/ health facilities. Ii) make the electronic data source more comprehensive and more accessible | 2 | i) Establish hard copies resource centers for health at national/ regional/ facility level. ii) make the electronic data source more comprehensive and more accessible | MOH | UN partners, PEPFAR and USG partners, World Bank, |  | X | X | X | $100,000 | $10,000 | 90000 |  | Technical assistance for national observatory/portal
| b. Make summarised reports in siswati and disseminate to communities annually. | 4 | Technical assistance for a siswati linguist workshop for 10 people x 5 days and printing of documents | MOH | UN partners, PEPFAR and USG partners, World Bank, |  |  | X |  | $7000 | $0 | 7000
| #REF! | [10 empty] | 0
50% | MATERNAL DEATH SURVEILLANCE AND RESPONSE
4 | [11 empty] | 0 |  | Workshop for mobilisation of key decision makers |  | 70000
3 | Strengthen national capacity through training in MDSR including neonatal death audits ICD 10 | 1 | Revise the MDR committee TORs to include MNDSR and IDSR for pushing the agenda on MNDSR activities | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  | x |  |  | 500 | 0 | 500
|  | 1 | Adapt Regional generic MDSR guidelines( to include the perinatal) by the National core team, with WHO external TA needed Printing of the National MNDSR Guidelines | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x |  | 35000 | 15000 | 20000
|  | 1 | Update the existing perinatal deaths reporting forms to include Maternal and perinatal Deaths reporting and action to be taken (response) | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x | [5 empty] | National capacity building workshops
3 |  | 1 | Conduct national TOT capacity building workshop with WHO external TA needed | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x |  | 20000 | 10000 | 10000 |  | District capacity building workshops
3 | The four regional committees have just been recently constituted there is need for capacity building through training in MNDSR and ICD 10 | 2 | Conduct regional capacity building workshops for health workers with WHO external TA needed | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x | x | 40000 | 30000 | 10000
| Integrate MNDSR with IDSR in notification and surveillance | 2 | Orient IDSR program staff on MNDSR | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x | x | 500 | 0 | 500
2 | Provide supportive supervision & mentoring of HCW on MDSR, Train providers on the guidelines, Conduct National & Regional data meeting to share best practices to motivate HCWs Improve reporting by hospitals; Training in ICD 10 coding certification and coding (links with CRVS) | 2 | Train Doctors, CRVS staff and data clerks (from public and private sectors) in ICD 10 coding & link with CRVS unit WHO external TA needed | MOH & MOHA | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x | x | 0 | 0 | 0 |  | Training of hospital staff in ICD and coding (link with CRVS)
2 | Strengthen hospital capacity and practices, including private sector in reviewing all maternal and neonatal deaths | 2 | Support and mentor facilities in completion of maternal neonatal death reporting forms and timely submission | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x | x | 20000 | 10000 | 10000 |  | Routine reviews/audits
| #REF! | [10 empty] | 0
| Conduct quality of care assessment in maternity care facilities | 1 | undertake quality of care assessment in a representative number of maternity facilities WHO external TA needed link with M&E | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  |  | x | 20000 | 0 | 20000 |  | Technical assistance and training for facility assessment
| #REF! | [10 empty] | 0
3 | Conduct supportive supervision and mentoring for the focal persons at chiefdom level. Create awareness at community level to report all maternal and neonatal deaths within 24hrs to the responsible persons at national level (contacts given). Can use existing 977 system. | 1 | Orient communities on the need of reporting all deaths within 24 hours using existing structures including 977 toll free line | MOH, MOT and Parliament | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x |  | 30000 | 5000 | 25000
2 | Strengthen the existing system of maternal and neonatal deaths reporting and initiation of response by electronic devices | 1 | Train community focal persons on reporting of maternal and neonatal emergencies using ICT and toll free lines | MOH, | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x | x | 15000 | 0 | 15000 |  | Develop plan for strengthening MDSR in community
2 | Finalize the VA forms and train the SRH regional mentors to conduct VAs on maternal and neonatal deaths in communities. | 1 | Train health care workers on use of verbal autopsy tools | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x |  |  |  | 0 |  | Introduce/train on community reporting using ICT
1 | Develop a system of involving communities in verbal autopsies and response | 1 | Sensitize communities on the need for verbal autopsies | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  |  | x |  | 10000 | 0 | 10000 |  | Training on VA at community level
| #REF! |  | #REF! | [8 empty] | 0 |  | Develop system for review process and feedback/interpretation of data
| #REF! | [10 empty] | 0
1 | Initiate and institutionalize annual review of surveillance and response system for maternal and new born deaths including timely dissemination and use of the report | 1 | Conduct annual reviews on maternal and neonatal deaths and response system | MOH | WHO, UNFPA, UNICEF, EGPAF,ICAP,WB, UNDP, USG, |  | x | x | x | 500 | 0 | 500
| #REF! | [10 empty] | 0 |  | Monitoring and evaluation of coverage of MDSR, quality of reviews, recommendations and actions
| #REF! | [10 empty] | 0
27.78% | INNOVATION AND E-HEALTH | [13 empty] | E
1 | To develop eHealth Policy and Strategy | 1 | The Directorate develop eHealth policy and strategy, based on experiences from peer countries. The process is overseen by the office of the Deputy Director of Health Services. | MoH (Directorate, SID, SRH), eGov Unit | WHO, UNDP |  | x | x |  | 24736.8421 | 9500 | 15236.8421 |  |  | 235000
1 | Incorporate MNCH in the policy that is to be developed | 2 | same as above | MOH (SRH) |  |  | x | x |  |  |  | 0
| #REF! |  | #REF! | [8 empty] | 0
2 | Determine desired outcomes and priorities for infrastructure deployment to support health services delivery and information flows. | 2 | Assess infrastructure status for priority information systems coverage, status, and functioning; develop action plan in line with overall national goals. This should be done with health and ICT sector participation and in the context of a national planning exercise. | Moh(SID), Govt Comp Services |  |  | x |  |  | 421052.6316 |  | 421052.6316 |  |  | 4000000
2 | Strengthen and scale up of connectivity and infrastructure and Community based health volunteers to have access to connectivity gadgets to communicate to the emergency task force. | 2 | Tap into existing networks which are used by government departments, eg Fire Department. Need to acquire relevant equipment for signal transmission. | Moh(SID), Govt Comp Services |  |  | x | x | x | 157894.7368 |  | 157894.7368 |  |  | 1500000
2 | Capacity building for users including the community care volunteers | 1 | Train users at all levels and their role to support this initiative on their day to day activities. | MoH (SID, SRH, RHM) |  |  |  | x |  | 5263.1579 |  | 5263.1579 |  |  | 50000
2 | Determine the eHealth services required to support the country’s priority programs and goals, particularly with respect to information flows. | 1 | Assess the services and applications being implemented across the sector, and any opportunities this provides. This should be done with health and ICT sector participation and in the context of a national planning exercise. | MoH(Directorate) |  |  | x | x |  | 10526.3158 |  | 10526.3158 |  |  | 100000
2 | Reporting system needs to be strengthened by providing mentoring and supportive supervision to the facilities | 2 | Use of RHMTs, Nurse Managers, Public health and Clinical meetings. Use health forums eg Child Health Forum | MoH(Directorate, SHA), DPM(NCCU) |  |  | x | x | x | 10526.3158 |  | 10526.3158 |  |  | 100000
2 | Scale up data sharing through the use of government website by giving access to programmes to upload reports. | 1 | Use the govt website to post available reports. Give easier access for the programs to upload reports. | MoH(Communication Office), eGov Unit |  |  | x |  |  | 0 |  | 0 |  |  | 0
| #REF! |  | #REF! | [6 empty] | 0 |  | 0
3 | Document and disseminate theexisting Health Information systems standards and interoperability components required to support eHealth services, applications and infrastructure, as well as to support broader changes to health information flows. | 2 | The selection, agreement and adoption of standards should be linked to the improvement of priority services and systems. This foundational step should be done in the context of national eHealth planning. | MoH (Directorate, SID) SWASA |  |  | x | x | x | 26315.7895 |  | 26315.7895 |  |  | 250000
1 | Review the HIS standards and guidelines to meet the current technology trend | 1 | Involve SWASA in the review and coding of the standards | MoH (QA, SID, SRH), Govt Comp Services, Egov Unit, Swasa |  |  | x | x |  |  |  | 0
| #REF! |  | #REF! | [8 empty] | 0
1 | Finalise the establishment and support of a strong effective eHealth coordination mechanism. Establish a national steering group for eHealth, supported by a project team with planning skills and knowledge of eHealth. Assess which organizations or groups are active in eHealth, and their potential role in the development of a national eHealth program. | 2 | Establish a national steering group for eHealth, supported by a project team with planning skills and knowledge of eHealth. Assess which organizations or groups are active in eHealth, and their potential role in the development of a national eHealth program. | MoH (Directorate, SID), Egov Unit, |  |  | x | x |  | 6315.7895 |  | 6315.7895 |  |  | 60000
| #REF! |  | #REF! | [8 empty] | 0
| #REF! |  | #REF! | [8 empty] | 0
2 | Develop policies and guidelines. Assure health sector, ministerial and government leadership and support. Ensure that the required program development skills and expertise are available. | 1 | Assess current legislation, regulation and policies for their appropriateness and potential revision towards supporting improved eHealth environment. This should take place in the context of a national eHealth planning process. Develop data protection policies and guidelines. Assure health sector, ministerial and government leadership and support. Ensure that the required program development skills and expertise are available. | [6 empty] | 24736.8421 |  | 24736.8421 |  |  | 235000
2 | Enforce compliance to data protection policies | 2 | Implement the standards of practice for health workers at all level. | MoH (QA, SID, SRH) |  |  | x | x |  | 0 |  | 0 |  |  | 0
| #REF! |  | #REF! | [8 empty] | 0
| #REF! |  | #REF! | [8 empty] | 0
6.667% | MONITORING OF RESOURCES
1 | Sensitize high level ministry and other relevant stakeholder ministry officials on the recommended NHA Framework named System of Health Accounts 2011 (SHA 2011) | 1 | Organize a half day meeting to sensitize high level ministry and other relevant stakeholder ministry officials on the NHA Framework | PLANNING UNIT | WHO |  |  | X |  |  | 1000 | -1000 |  | Apply/validate one national health accounts framework |  | 53000
| Organize a meeting to engage government and development partners and work towards a "compact" which requires all development partners, NGOs and other stakeholders in the health sector to report data on health expenditures and results regularly and in a standarised format. | [10 empty] | 0 |  | Stakeholder workshop to establish governance and TOR
0
2 | Organize a meeting to engage government and development partners and work towards "compact" | 1 | Organize a one day meeting to sensitize govt and development partners, business representatives, civil society, etc on the NHA (TA required from WHO to support this activity) | PLANNING UNIT | WHO |  |  | X |  |  | 5000 | -5000
[12 empty] | 0 |  | TA (via IHP+) for the development of a "compact"
0
1 | Set up a steering committee, officially approved, with institutional support, and functioning using results-based management methods | 1 | Hold stakeholder meeting to set up steering committee. Conduct regular meetings of technical steering committee | PLANNING UNIT | WHO |  |  | X |  |  | 0 | 0
1 | Ensure inclusion of all key stakeholders in resource tracking /NHA | 1 | Revisit and enter into a Memorandum Of Understanding with all the stakeholders (WHO can support the drafting of the MOU if requested) | PLANNING UNIT | WHO |  |  | X |  |  | 0 | 0 |  | Regular meetings of technical steeering committee
0
0
1 | Train NHA TWG on System of Health Accounts 2011 (SHA 2011). | 1 | Engage technical support and training in NHA for NHA TWG (TA from WHO required for this training) | PLANNING UNIT | WHO |  |  | X |  |  | 20000 | -20000
1 | Map government codes to NHA codes and develop IT conversion tool for NHA | 1 | Ensure the NHA Production Tool is used | PLANNING UNIT | WHO |  |  | X |  |  | 0 | 0 |  | Technical support and training in NHA at national and district level
1 | Develop database for production of NHA | 1 | Consultant for development of database | PLANNING UNIT | WHO |  |  | x |  |  | 10000 | -10000 |  | Development of IT tool for mapping and conversion of data to NHA
[12 empty] | 0 |  | Consultant for development of database
0
1 | Produce the NHA Report and analytical summaries | 1 | Publish NHA Report and policy briefs | PLANNING UNIT | WHO |  |  | x |  |  | 5000 | -5000
1 | Disseminate report and analyses on public website | 1 | Organise a launch workshop for NHA Report (TA may be required from WHO to support this activity) | PLANNING UNIT | WHO |  |  | x |  |  | 10000 | -10000 |  | Training workshops for production of reports
|  |  | Develop and maintain a website that is publicly available for the NHA Report (electronic), summaries and policy briefs | [7 empty] | 2000 | -2000 |  | Establish central website for dissemination of results (links with national observatory)
1 | Advocate for/promote the use of NHA data in the development of national policies. | 2 | Ensure policy makers, programme managers, etc, incorporate the NHA findings in the preparation of policies and plans | PLANNING UNIT | WHO |  |  |  | x |  | 0 | 0
[12 empty] | 0 |  | Meetings with policy makers to identify needs and integrationof NHA data in policy process
0
50% | REVIEW PROCESSES
2 | Undertake systematic multi-stakeholder annual reviews in line with goals, targets of the NHS and other national and global development priorities. Establish an independent monitoring and peer review mechanism to enhance validation and documentation of best practices | 1 | conduct a 3day workshop to develop an assesssment tool and prepare for the review. Identify monitoring and peer review team to validate and document best practices . | MoH | SRH Stakeholders (IATCC) |  |  | x | x | 40000 | 15000 | 25000 |  | Workshops to prepare for reviews including field visits
2 | Create a forum at national level for multi-stakeholder active participation and define processes, timelines and accountability mechanism to ensure better quality of the annual and periodic reviews | 1 | incorporate sharing of reviews in existing RMNCH IATCC | MOH | RMNCH Stakeholders |  |  | x |  | 0 | 0 | 0 |  | Use /apply process for assessing national planning process, such as IHP+ JANS
2 | Based on Annual Plans, develop a calendar to ensure that the RMNCH reviews are held as planned and findings are disseminated and used to inform programming and decision making. | 1 | Develop a calender for MNCH reviews. Conduct one day annual dissemination meeting findings | MOH | RMNCH Stakeholders |  |  | x |  | 700 | 0 | 700 |  | Prepare report of RMNCH review to inform health sector review
0
0
2 | Develop and implement in health training institutions, a training curriculum for health workers on health data management, M&E and reviews | 1 | Develop a M&E training curriculum for health workers (TA). Incorporate into the university curriculum. | MOH | RMNCH Stakeholders |  |  | x | x | 15000 | 0 | 15000 |  | Prepare and discuss good synthesis of results and information based on analytical report
| Develop and implement guiding principles and policies for comprehensive data collection and use beyond health facilities | 2 | Conduct 4 meetings to develop policies for collecting community based data | MOH |  |  |  | x |  | 4000 | 4000 | 0
0
3 | Establish a Task Team that oversees reviews and implementation of review findings and recommendations for planning purposes and informed decision making at all levels | 1 | Use the monitoring and review team to monitor implementation of review finding and recommendations | MOH | RMNCH Stakeholders |  | x | x |  | 0 | 0 | 0 |  | Translate the decisions/resource allocations into the annual operational planning process
3 | Enforce participation of all stakeholders in the annual reviews. | 2 | Hold a one day workshop to discuss accountability mechanisms for attending annual reviews | MoH |  |  |  | x |  | 500 | 500 | 0
0
0
3 | Develop an agreement framework for coordination of partners and implementation of the National Health Sector Establish a functional partner coordination Unit to lead planning, coordination and facilitation of all Development partners | 3 | Train partner coordination unit in effective leadership and coordination of partners (TA) | MOH | RMNCH Stakeholders |  |  | xx |  | 20000 | 0 | 20000 |  | IHP+ approach to develop compact
3 | Put in place effective systems and protocols for partner coordination to implement the health strategic plan |  | Monitoring and peer review team to conduct bi-annual internal reviews to monitor adherence to the NHS | MOH | RMNCH Stakeholders |  |  | x |  | 0 | 0 | 0 |  | Joint field visits as part of preparation of reviews
0
0
19.44% | ADVOCACY & OUTREACH
2 | Advocate for appointment of a focal person from parliament health portfolio committee for RMNCH issues. Develop a strong and effective information exchange mechanisms between the IATCC and the health portfolio committee | 2 | Prepare advocacy brief. Hold one day meeting with members of parliament to share the brief. Assist parliament to appoint a focal person from parliament health portfolio committee for RMNCH issues | MOH | Minister, Parliament Health Portfolio Committee, RMNCH Stakeholders |  | x | x |  | 700 | 0 | 700
1 | Establish forums for public hearings and information sharing on RMNCH. Sensitize Parliamentarians on RHMNCH issues through Health Portfolio Committee | 2 | Conduct periodic dissemination/feedback & information sharing meetings/seminars | MOH | Minister, Parliament Health Portfolio Committee, RMNCH Stakeholders |  |  | x |  | 4000 | 0 | 4000
0
0
3 | Establish forum for Task Force to interact with Parliament. Establish a functional office for the Task Force. Develop, implement and monitor Task Force Strategic plan | 1 | Consultancy for development of Policies and Strategic Plan. Establishing the Secretariat office of the Task Force (TA) | MoH | SRH Civil Society Task Force |  |  | x | x | 15000 | 0 | 15000
2 | Train Civil Society SRH Task Force for effective coordination and advocacy through results-based approach. | 2 | Training of Task Force on advocacy | MoH | SRH Civil Society Task Force |  |  | x |  | 2100 | 0 | 2100
0
0
2 | Conduct workshops and meetings for the media on accurate, responsive and responsible reporting on RMNCH related issues | 3 | media training/workshop for 2 day | MoH /SRH/Media Focal Person | MISA?Media |  |  | x | x | 1400 | 0 | 1400
1 | Work with the media to report on the monitoring and implementation of the Global Strategy | 1 | Meetings, Press Briefings and Conferences | MoH/ SRH/ Media Focal Person/Civil Society Task Force | MISA/Media |  |  | x | x | 0 | 0 | 0
1 | Plan and conduct meeting with media to improve information flow. | 3 | Meetings, Press Briefings and Conferences | MoH/ SRH/ Media Focal Person/Civil Society Task Force | MISA/Media |  |  | x | x | 0 | 0 | 0
0
0
1 | Conduct count down activities/agenda such as RMNCH annual conference/indaba for advocacy, public awareness, and updates | 1 | RMNCH Conference/Indaba | MoH/SRH Committee | SRH Stakeholders |  | x | x | x | 33000 | 0 | 33000
1 | Prepare Countdown report / profile updates that are evidence based. | 1 | Workshops | MoH/SRH Committe | SRH Stakeholders |  |  | x | x | 3000 | 3000 | 0
0
0
[5 empty] | Total Estimated Cost |  |  |  |  | 1333635.1211
[5 empty] | Catalytic funding (total max. amount $250k) | [5 empty] | 250000
[5 empty] | Unfunded balance | [6 empty] | 1227078.4211